## Issue-Updated
S.NO | Description | Remarks | Dev Status | Status
1 | While change the address in location details ( input string was not in correct format )error occurs. |  | Fixed | Closed
2 | Premises details address search is not working. |  |  | Closed
3 | Once caluculate premium generated, again change the floor sq, calculate premium not calculating. | Unable to edit the floor area after RFQ generate. Input 32 string error occurs | Fixed | Closed
4 | Premium with Taxes displaying wrong. | After RFQ Generated, Edit floor area or address and click svae btn ( Something went wrong: REF00000145) error occurs |  | Closed
5 | Fill basic cover and click calculate premium, then again add basic cover &click save. First recored will be hide. | Fill any details in extension and click save button, and again open the covers tab, all the records will be deleted. | Fixed | Closed
6 | Delete the added cover and again add new cover details , System still showing old data. |  | Fixed | Closed
7 | While edit floor area ( input string 32 error occurs ). |  | Fixed | Closed
8 | Builidng permit , Basic cover COMBINED SINGLE LIMIT FOR TPBI & TPPD defaulty add as 0 premium . |  | NA | Closed
9 | Building permit MUNTINLUPA PREMIUM RATES mismatch. |  |  | Closed
10 | Changing Policy Group from CGL / Annual aggregate : PML, Pml amout not clear. |  | NA
11 | Annual aggregate>SUPPLEMENTARY FIRST AID PAYMENTS> Unable to delete the added record in basic cover |  | Fixed | closed
12 | Alredy basic cover added but still system ask to add alteast one record. | 1. Frist add csl cover > calculate premium and delete the location, then change the Policy Group as Annual aggregate.(Alredy basic cover added but still system ask to add alteast one record.) error occurs. 2. Again if Policy Group change to CGL , policy cover have no records found error occurs. | Fixed | Closed
13 | Once click on convert proposal system displaying an alert message as "Something went wrong: REF00000118" | After RFQ Generated, Edit floor area or address and click svae btn ( Something went wrong: REF00000145) error occurs | Fixed | Closed
14 | Policy Preview: The remote server returned an error: (500) Internal Server Error.
15 | CSL > Purpose Type: Others > Add extention cover > (Input string was not in a correct format.Couldn't store <10.0% of the loss, minimum of Php 5,000.00 for each and every loss (For Third Party Property Damage Only)> in SMIId Column. Expected type is Int32.) Error occurs. | Cover not saved ( Add Cover Details For Location: 1) Error occurs. |  | Closed
16 | Annual Aggregate > TPPBI & TPPD LIABILITY > Rate should not be allow to enter more than 10 % | Need confirmation with nijanthan |  | Closed
17 | Error occurs while change the location . Even I delete the location and add again , still system throws error: Delete the location and add |  | Fixed | Closed
18 | Annual Aggregate > Bussiness permit > cover added , but system throws error: Add Cover Details For Location: 1 | Note: Default cover automaticaly removed while click calculate premium button. | Fixed | Closed
19 | In Edit flow > Proposal Type is removed. Unable to continue the flow | After quote Generated, close the lead and again continue the lead in dashboard. Proposal type value is removed. |  | Open
20 | Annual aggregate>SUPPLEMENTARY FIRST AID PAYMENTS>Enter and clear the record , while click the save button System throws an error Add/Clear Cover Records. |  |  | Closed
21 | Edit location, Error: Undefined occurs. | when issue 20 comes, after edit the location Error: Undefined occurs. |  | closed
22 | Mulitple locations added. | Annual aggregate > Building permit > calculate premium and again change the purpose type as > others. System can able to add multiple locations. |  | Open
23 | CSL > Purpose Type: Others, Bulding Permit & Annual aggerate . System accepts floor area as 0.,also calculates premium. | discus with nijanthan. |  | Open
24 | SUPPLEMENTARY FIRST AID PAYMENTS > Currently System not allow to enter rate 0, System should accepct the rate 0. | Refer CGL Basic Cover & Extension sheet will discuss |  | Open
25 | SUPPLEMENTARY FIRST AID PAYMENTS > should have Limit per Occurrence, Limit per Person only | Refer CGL Basic Cover & Extension sheet will discuss |  | Open
26 | For Extension covers (AUTOMATIC ADDITIONS OF PREMISES, CONTIGENT LIABILITY FOR SUB-CONTRACTORS AND CONTRACTORS, TENANTS LIABILITY ENDORSEMENT, CONTIGENT LIABILITY FOR THE PROVISION OF THE TRANSPORTATION SERVICES, FIRE AND EXPLOSION ENDORSEMENT, LIABILITY DUE TO ARMED ROBBERY &/or IRRESISTIBLE FORCE, AUTOMATIC REINSTATEMENT OF LOSS, INDEPENDENT CONTRACTOR'S LIABILITY ENDORSEMENT, 72 HOURS SUDDEN AND ACCIDENTAL POLLUTION, CONTRACTUAL LIABILITY ENDORSEMENT, HEAT APPLICATION WARRANTY) Limit per occurance TPBI , limit per person, limit per occurrance TPPD are not applicable. | Refer CGL Basic Cover & Extension sheet will discuss |  | Open
27 | For Extension Covers ( FOOD AND DRINK POISONING ENDORSEMENT, PERSONAL INJURY AND ADVERTISING INJURY LIABILITY COVERAGE, PREMISES MEDICAL PAYMENTS ENDORSEMENT) Limit per Occurrence for TPPD not applicable. | Refer CGL Basic Cover & Extension sheet will discuss |  | Open
28 | For Extension cover GARAGE KEEPERS LIABILITY COVERAGE should have Limit per Occurrence only. | Refer CGL Basic Cover & Extension sheet will discuss |  | Open
29 | For Extension Covers ( CAR PARK LIABILITY CLAUSET, VALET PARKING CLAUSE, EXCESS AUTOMOBILE LIABILITY EXTENSION CLAUSE) Limit per Occurrence for TPPBI not applicable. | Refer CGL Basic Cover & Extension sheet will discuss |  | Open
30 |  | Refer CGL Basic Cover & Extension sheet will discuss |  | Open
31 | CAR PARK LIABILITY CLAUSE > (Limit per Occurrence for TPBI ) Not applicable. | Refer CGL Basic Cover & Extension sheet will discuss |  | Open
32 | WATER DAMAGE ENDORSEMENT > (Limit per Occurrence for TPPD ) Only applicable. | Refer CGL Basic Cover & Extension sheet will discuss |  | Open
33 | The Policy Schedule contents, such as the CAR product, need to be modified. | will Discuss |  | Open

## Screen shot
17
18

## Sheet1
14753.41 | 1844.18 | 1770.41 | 29.51 | 18397.51
14753.41 | 1844.1762 | 1770.4092 | 29.5068 | 18397.5023