## Review log
Review log
Project Name | NOVA-DIGITAL | Work Product ID | CMS changes to download the job details in excel format | Author | MOHANARANGAN RAGAVAN
Sprint No. | 4 | Reviewed on | 28/Aug/23 | Reviewer (s) | SARAVANAN PURUSHOTHAMAN
Review Report
S.No. | Review description | Review checklist reference | Phase injected in | Defect type | Fixed by | Fixed on | Fix Description | Status | Remarks
1 | Tooltip is required for DOB format DD/MM/YYYY |  | Coding | UI Related Defect | MOHANARANGAN RAGAVAN | 25/Aug/23 | Done | Closed
2 | Change the DataSet into Datatable for single table output |  | Coding | Logical Flow/Sequencing defect | MOHANARANGAN RAGAVAN | 25/Aug/24 | Done | Closed
3 | Change the Session Variable ValSubBranch instead of Hidden Field |  | Coding | UI Related Defect | MOHANARANGAN RAGAVAN | 25/Aug/25 | Done | Closed
4 | Relation Name should not allow numeric value |  | Coding | UI Related Defect | MOHANARANGAN RAGAVAN | 25/Aug/26 | Done | Closed

## Guideline
S. No | Phase | Defect Type | Description | S. No. | Defect Cause | Defect Cause Description
1 | Planning | Incorrect or Incomplete information | Incorrect or incomplete information provided in planning documents | 1 | Delayed Clarification | There can be scenarios wherein the clarifications required for urgent requests or requirements are received beyond the target date.
2 | Planning | Deviation from Standard Template | Deviation from QMS standard template. If tailoring approval is sought for using the project specific template, the template being used and template for which deviation is approved are not matching. This defect type is applicable in all the phase | 2 | Frequent Requirement Change | Frequent change in requirement led to this defect.
3 | Planning | Section not Filled | All sections not completely filled. This defect type is applicable in all the phase | 3 | Improper Communication | Misunderstanding what was wanted. Either you misread the design document or did not understand the requirements.
4 | Planning | Any Other | Any other Type of defects | 4 | Inadequate Process | A fault in your process led you to do the wrong thing
5 | Requirements | Incorrect Requirements | Requirements are documented incorrectly in the requirement document. This defect type is applicable in requirement phase | 5 | Inadequate Review | So it is a simple case of oversight or goof.
6 | Requirements | Missing or Incomplete Requirements | Requirements are missed out in the requirements document or additional inputs are required for the requirements to complete the requirement document. | 6 | Inadequate Skill Level | Project teams not skilled to execute the projects based on Specific technology / Domain
7 | Requirements | Deviation from Standard Template | Deviation from QMS standard template. If tailoring approval is sought for using the project specific template, the template being used and template for which deviation is approved are not matching. This defect type is applicable in all the phase | 7 | Inadequate Training / Education/ Awareness | Inadequacies have occurred due to education, training, lack of domain knowledge etc.
8 | Requirements | Section not Filled | All sections not completely filled. This defect type is applicable in all the phase | 8 | Insufficient Testing | Testing not adequate done for the project to satisfy the project requirements
9 | Requirements | Any Other | Any other Type of defects
10 | Design | Incorrect Design | Design approach is not as per the requirements stated in the requirements document. This defect type is applicable in design phase
11 | Design | Interface Design Errors | Design documented has improper interface definition and descriptions. (This is related to application interface definition / description and not related to user interface). This defect type is applicable in design phase
12 | Design | Deviation from Standard Template | Deviation from QMS standard template. If tailoring approval is sought for using the project specific template, the template being used and template for which deviation is approved are not matching. This defect type is applicable in all the phase
| Design | Deviation from Design Standards | Design documented is not as per the design standards defined /followed in the project. This defect type is applicable in design phase
13 | Design | Section not Filled | All sections not completely filled. This defect type is applicable in all the phase
14 | Design | Any Other | Any other Type of defects
15 | Coding | Code not Modular | Code not organized properly and number of lines in the functions is more than as specified in coding guidelines.
16 | Coding | Deviation from Coding Standards | Non adherence to coding guidelines defined/followed in project. This defect type is applicable in coding phase
17 | Coding | Logical Flow/Sequencing defect | The logical flow mentioned in the code not in correct sequence and not as per logic defined in the design document. This defect type is applicable in coding phase
| Coding | UI Related Defect | Incorrect positioning of messages on the screen Incorrect alignment of components on screen Grammatical/Spelling mistakes Font colour/size not matching the customer requirements Browser compatibility related issues
18 | Coding | Section not Filled | All sections not completely filled. This defect type is applicable in all the phase
19 | Coding | Any Other | Any other Type of defects
20 | Testing | Incomplete or Incorrect Test Plan | Test Plan are not addressing all design aspects or test strategy included in the test plan for testing the requirements is not correct. This defect type is applicable in testing phase
21 | Testing | Missing or Incorrect Test Case | It does not include the test case for testing all the requirements or Test steps / scenarios included for testing the requirements / design are not correct. This defect type is applicable in testing phase
22 | Testing | Incomplete or Incorrect Test Data | Test data created for testing is not complete or is not correct, This defect type is applicable in testing phase
23 | Testing | Any Other | Any other Type of defects
24 | Testing | Deviation from Standard Template | Deviation from QMS standard template. If tailoring approval is sought for using the project specific template, the template being used and template for which deviation is approved are not matching. This defect type is applicable in all the phase
25 | Testing | Section not Filled | All sections not completely filled. This defect type is applicable in all the phase