## Revision History
Revision History
Version No | Date | Reason For Changes | Author | Reviewer | Approver
0.01 | 2023-08-25 | Draft | RAVI
Test Case Information
Sl.No | Test case ID | Test Case Objective | Status | Test Scenario Link
1 | TC-F-CMS_001 | To check all the functionalities of Download the Upoad CVs in excel format | Pass | TS-CMS_001

## Functional Test Case
Test Case Basic Information
Project Name : | NOVA-DIGITAL-SCRUM
Screen Name : | CMS
Pre Requisite : | CMS changes to download the job details in excel format. | [6 empty] | Testing Type : | System Integration Testing |  |  |  | System Integration Testing
Instructions : | [8 empty] | Cycle 1 |  |  |  | Cycle 2
Testcase ID | Step No. | Sprint Number | User Story | Input Specification | Help / Remarks | Input/Test Data | Expected Result | Actual Result | (Pass/Fail) | Tested By | Tested Date : | Defect Id | (Pass/Fail) | Tested By | Tested Date : | Defect Id
TS-CMS_001 : To check all the functionalities in City landing pages.
TC-F-CMS_001 | TC-F-CMS_001 | 4 | NOVDIGSCR-316 | To check the functionality of " Job Apply Details " in CMS. |  | <click> | System should open the Job apply details page. | System is open the Job apply details page. | PASS | RAVI | 2023-08-25 |  | PASS | RAVI | 2023-08-26
TC-F-CMS_002 | TC-F-CMS_002 | 4 | NOVDIGSCR-316 | To check the functionality of " Job Type " Dropdown. |  | <click> | System should the list of Job tyoes . | System is the list of Job tyoes . | PASS | RAVI | 2023-08-25 |  | PASS | RAVI | 2023-08-26
TC-F-CMS_003 | TC-F-CMS_003 | 4 | NOVDIGSCR-316 | To verify the " Job Type Dropdown " with valid data rom dropdown. |  | MARKETING - NON BANKING FINANCIAL CORPORATION | System should accept the user given input. | System is accept the user given input. | PASS | RAVI | 2023-08-25 |  | PASS | RAVI | 2023-08-26
TC-F-CMS_004 | TC-F-CMS_004 | 4 | NOVDIGSCR-316 | To verify the " Job Type Dropdown " with valid data rom dropdown. |  | MARKETING - NON MOTOR (SME) | System should accept the user given input. | System is accept the user given input. | PASS | RAVI | 2023-08-25 |  | PASS | RAVI | 2023-08-26
TC-F-CMS_005 | TC-F-CMS_005 | 4 | NOVDIGSCR-316 | To verify the " Job Type Dropdown " with valid data rom dropdown. |  | MARKETING - RETAIL BROKING | System should accept the user given input. | System is accept the user given input. | PASS | RAVI | 2023-08-25 |  | PASS | RAVI | 2023-08-26
TC-F-CMS_006 | TC-F-CMS_006 | 4 | NOVDIGSCR-316 | To verify the " Job Type Dropdown " with valid data rom dropdown. |  | ACCOUNTS | System should accept the user given input. | System is accept the user given input. | PASS | RAVI | 2023-08-25 |  | PASS | RAVI | 2023-08-26
TC-F-CMS_007 | TC-F-CMS_007 | 4 | NOVDIGSCR-316 | To verify the " Job Type Dropdown " with valid data rom dropdown. |  | HUMAN RESOURCE | System should accept the user given input. | System is accept the user given input. | PASS | RAVI | 2023-08-25 |  | PASS | RAVI | 2023-08-26
TC-F-CMS_008 | TC-F-CMS_008 | 4 | NOVDIGSCR-316 | To verify the " Job Type Dropdown " with valid data rom dropdown. |  | ADMINISTRATOR | System should accept the user given input. | System is accept the user given input. | PASS | RAVI | 2023-08-25 |  | PASS | RAVI | 2023-08-26
TC-F-CMS_009 | TC-F-CMS_009 | 4 | NOVDIGSCR-316 | To verify the " From Date " with valid data. |  | 2023-01-07 | System should accept the user given input. | System is accept the user given input. | PASS | RAVI | 2023-08-25 |  | PASS | RAVI | 2023-08-26
TC-F-CMS_010 | TC-F-CMS_010 | 4 | NOVDIGSCR-316 | To verify the " To Date " with Valid Data. |  | 31-08-2023 | System should accept the user given input. | System is accept the user given input. | PASS | RAVI | 2023-08-25 |  | PASS | RAVI | 2023-08-26
TC-F-CMS_011 | TC-F-CMS_011 | 4 | NOVDIGSCR-316 | To Verify the Functionality of "From" and "To" Date. |  | 01-07-2023 TO 31-08-2023 | From date should be less than To date. | System is accept the user given input. | PASS | RAVI | 2023-08-25 |  | PASS | RAVI | 2023-08-26
TC-F-CMS_012 | TC-F-CMS_012 | 4 | NOVDIGSCR-316 | To Verify the functionality of " Submit " Button. |  | <click> | 1. Select Job Type 2. choose start date and end date. After Click submit button, System shhould show the respected list. | System is not show the respected list. | FAIL | RAVI | 2023-08-25 | 1 | PASS | RAVI | 2023-08-26
TC-F-CMS_013 | TC-F-CMS_013 | 4 | NOVDIGSCR-316 | To Verify the functionality of " Clear" Button. |  | <click> | System should clear the user choosen job list. | System is clear the user choosen job list. | PASS | RAVI | 2023-08-25 |  | PASS | RAVI | 2023-08-26
TC-F-CMS_014 | TC-F-CMS_014 | 4 | NOVDIGSCR-316 | To Verify the functionality of " Download" Button. |  | <click> | 1. Select Job Type 2. choose start date and end date. 3. Clik Submit Button System should download the respective files with ( Excel Format ) | System is not download the respective files with ( Excel Format ) | FAIL | RAVI | 2023-08-25 | 2 | PASS | RAVI | 2023-08-26
TC-F-CMS_015 | TC-F-CMS_015 | 4 | NOVDIGSCR-316 | To Verify the functionality of " Resume " Button. |  | <click> | System should download the Resume ( as PDF file ) | System is not download the Resume ( as PDF file ) | FAIL | RAVI | 2023-08-25 | 3 | PASS | RAVI | 2023-08-26
TC-F-CMS_016 | TC-F-CMS_016 | 4 | NOVDIGSCR-316 | To Verify the functionality of " CV Download " Button. |  | <click> | 1. Select Job Type 2. choose start date and end date. 3. Clik Submit Button System Should Download the Cv ( as Rar File ) | System is not Download the Cv ( as Rar File ) | FAIL | RAVI | 2023-08-25 | 4 | PASS | RAVI | 2023-08-26