## Revision History
Revision History
Version No | Date | Reason For Changes | Author | Reviewer | Approver
0.01 | 2023-09-23 | Draft | RAVI
Test Case Information
Sl.No | Test case ID | Test Case Objective | Status | Test Scenario Link
1 | TC-F-FW_EV_001 | check all the functionalities in New FW EV landing page. | Pass | TS-FW_EV_001
2 | TC-F-FW_EV_002 | check all the Design in New FW EV landing page . | Pass | TS-FW_EV_002
3 | TC-C-FW_EV_001 | check all the Components in FW EV Landing Page. | Pass | TS-FW_EV_003

## Functional Test Case
Test Case Basic Information
Project Name : | NOVA-DIGITAL-SCRUM
Screen Name : | FW EV NEW LANING PAGE
Pre Requisite : | New FW Landing Page for EV Vehicle | [6 empty] | Testing Type : | System Integration Testing |  |  |  | System Integration Testing
Instructions : | [8 empty] | Cycle 1 |  |  |  | Cycle 2
Testcase ID | Step No. | Sprint Number | User Story | Input Specification | Help / Remarks | Input/Test Data | Expected Result | Actual Result | (Pass/Fail) | Tested By | Tested Date : | Defect Id | (Pass/Fail) | Tested By | Tested Date : | Defect Id
TC-F-FW-EV_001 : To check all the functionalities in FW EV New Landing Page.
TC-F-FW_EV_001 | TC-F-FW_EV_001_01 | 6 | NOVDIGSCR-664 | To check the functionality of the field " REGISTRATION NUM " in city landing page. |  | TN18U3663 | Systen should accept the user enterd input. | System is accepting the user enter input. | PASS | RAVI | 2023-09-27 |  |  | RAVI
TC-F-FW_EV_001 | TC-F-FW_EV_001_02 | 6 | NOVDIGSCR-664 | To check the functionality of the field " MOBILE NUM " in city landing page. |  | 7010314203 | System should accept the user enterd input. | System is accepting the user enter input. | PASS | RAVI | 2023-09-27 |  |  | RAVI
TC-F-FW_EV_001 | TC-F-FW_EV_001_03 | 6 | NOVDIGSCR-664 | To check the functionality of " NOT SURE OF YOUR CAR NUM " Button. |  | <click> | System should populate the without registration flow. | System is populate the without registration flow. | PASS | RAVI | 2023-09-27 |  |  | RAVI
TC-F-FW_EV_001 | TC-F-FW_EV_001_04 | 6 | NOVDIGSCR-664 | To check the functionality of " INSURE NEW CAR " Button. |  | <click> | System should populate the new flow. | System is populate the new flow. | PASS | RAVI | 2023-09-27 |  |  | RAVI
TC-F-FW_EV_001 | TC-F-FW_EV_001_05 | 6 | NOVDIGSCR-664 | To check the functionality of " I KNOW MY CAR NUM " Button. |  | <click> | System should populate the with registration flow. | System is populate the with registration flow. | PASS | RAVI | 2023-09-27 |  |  | RAVI
TC-F-FW_EV_001 | TC-F-FW_EV_001_06 | 6 | NOVDIGSCR-664 | To check the functionality of " TERMS AND CONDITION " Button. |  | <click> | System should redirect to Terms and Condition page. | System is redirect to Terms and Condition page. | PASS | RAVI | 2023-09-27 |  |  | RAVI
TC-F-FW_EV_001 | TC-F-FW_EV_001_07 | 6 | NOVDIGSCR-664 | To check the functionality of " INSURE NOW " Button. |  | <click> | System should move to OTP page. | System is moving to the OTP page. | PASS | RAVI | 2023-09-27 |  |  | RAVI
TC-F-FW_EV_001 | TC-F-FW_EV_001_08 | 6 | NOVDIGSCR-664 | To check the functionality of " RENEW SHRIRAM POLICY " Button. |  | <click> | System should redirect to Renew Shriram Policy page. | System is redirect to Renew Shriram Policy page. | PASS | RAVI | 2023-09-27 |  |  | RAVI
TC-F-FW_EV_001 | TC-F-FW_EV_001_09 | 6 | NOVDIGSCR-664 | To Check the functionality of " Key Features of Shriram Electric Car Insurance " forwar/backward arrow buton. |  | <click> | System Should slide the respective key features. | System is Slide the respective key features. | PASS | RAVI | 2023-09-27 |  |  | RAVI
TC-F-FW_EV_001 | TC-F-FW_EV_001_10 | 6 | NOVDIGSCR-664 | To check the Funtionality of " How to File a Claim for an Electric Car Insurance? " INTIMATE CLAIM button. |  | <click> | System should redirect to claim page. | Insure now button is Not working. | FAIL | RAVI | 2023-09-27 | NOVDIGSCR-721 |  | RAVI
TC-F-FW_EV_001 | TC-F-FW_EV_001_11 | 6 | NOVDIGSCR-664 | To Check the Funtionality of " Steps to Download Your Electric Car Insurance Policy " DOWNLOAD POLICY Button. |  | <click> | System Should redirect to Download Policy Button. | Download Policy Button is Not working. | FAIL | RAVI | 2023-09-27 | NOVDIGSCR-722 |  | RAVI
TC-F-FW_EV_001 | TC-F-FW_EV_001_12 | 6 | NOVDIGSCR-664 | To Check the functionality of Footer. |  | <click> | System Should redirect to the respective page. | Click Function not Working in MOBILE VIEW | FAIL | RAVI | 2023-09-27 | NOVDIGSCR-723 |  | RAVI
TC-F-FW_EV_001 | TC-F-FW_EV_001_13 | 6 | NOVDIGSCR-664 | To check the functionality of "quick renewal " Button. |  | <click> | System Should redirect to the quick renewal page | In Mobile view Quick renewal buton missing | FAIL | RAVI | 2023-09-28 | NOVDIGSCR-735 |  | RAVI
TC-F-FW-EV_002 : To check all the Design in FW EV New Landing Page.
TC-F-FW_EV_002 | TC-F-FW_EV_002_01 | 6 | NOVDIGSCR-664 | To Check the " NOT SURE OF YOUR CAR NUM " Dropdown . |  | <click> | Design should be as per Figma. | City Dropdown list is transparent. | FAIL | RAVI | 2023-09-27 | NOVDIGSCR-724 |  | RAVI | 2023-08-27
TC-F-FW_EV_002 | TC-F-FW_EV_002_02 | 6 | NOVDIGSCR-664 | To Check the " New Car Num " Dropdown. |  | <click> | Design should be as per Figma. | City Dropdown list is transparent. | FAIL | RAVI | 2023-09-27 | NOVDIGSCR-725 |  | RAVI | 2023-08-27
TC-F-FW_EV_002 | TC-F-FW_EV_002_03 | 6 | NOVDIGSCR-664 | To Check the Contact Button. |  | <click> | Design should be as per Figma. | Fields Not Aligned. In Mobile view , it overlaps while scroll the page . | FAIL | RAVI | 2023-09-27 | NOVDIGSCR-726 |  | RAVI | 2023-08-27
TC-F-FW_EV_002 | TC-F-FW_EV_002_04 | 6 | NOVDIGSCR-664 | To Check the " Key Features of Shriram Electric Car Insurance" Design. |  | <click> <slide> | Design should be as per Figma. | Forward , Backword arrow Button Missing in Mobile View. | FAIL | RAVI | 2023-09-27 | NOVDIGSCR-727 |  | RAVI
TC-F-FW_EV_002 | TC-F-FW_EV_002_05 | 6 | NOVDIGSCR-664 | To check " Electric Car Insurance: What's Not Covered? " Deisgn. |  | <click> <slide> | Design should be as per Figma. | In Figma It have slider, But in Uat It placed one by one, | FAIL | RAVI | 2023-09-27 | NOVDIGSCR-728 |  | RAVI
TC-F-FW_EV_002 | TC-F-FW_EV_002_06 | 6 | NOVDIGSCR-664 | To check " Insurance Coverage Options for Your Electric Car " Design. |  | <click> <slide> | Design should be as per Figma. | Insure now button is Missing , and It have slider, But in Uat It placed one by one, | FAIL | RAVI | 2023-09-27 | NOVDIGSCR-729 |  | RAVI
TC-F-FW_EV_002 | TC-F-FW_EV_002_07 | 6 | NOVDIGSCR-664 | To Check the "Add-ons for Electric Car Insurance" Design |  | <click> <slide> | Design should be as per Figma. | In Figma it mentioned as " Add-ons in Electric Vehicle Insurance for Enhanced Protection" . Also Slider is missing. | FAIL | RAVI | 2023-09-27 | NOVDIGSCR-730 |  | RAVI
TC-F-FW_EV_002 | TC-F-FW_EV_002_08 | 6 | NOVDIGSCR-664 | To Check "Steps to Download Your Electric Car Insurance Policy" Design. |  | <click> <slide> | Design should be as per Figma. | Currently it is Left aligned, it should be center aligned as per figma. | FAIL | RAVI | 2023-09-27 | NOVDIGSCR-731 |  | RAVI
TC-F-FW_EV_002 | TC-F-FW_EV_002_09 | 6 | NOVDIGSCR-664 | To check " How to Calculate Electric Car Insurance Premiums? " Design. |  | <click> <slide> | Design should be as per Figma. | In Figma It have slider, But in Uat It placed one by one, | FAIL | RAVI | 2023-09-27 | NOVDIGSCR-732 |  | RAVI
TC-F-FW_EV_002 | TC-F-FW_EV_002_10 | 6 | NOVDIGSCR-664 | To check " Documents Required for Electric Car Insurance Claim at Shriram General Insurance " Design. |  | <click> <slide> | Design should be as per Figma. | In Figma It have slider, But in Uat It placed one by one, | FAIL | RAVI | 2023-09-27 | NOVDIGSCR-733 |  | RAVI
TC-F-FW_EV_002 | TC-F-FW_EV_002_11 | 6 | NOVDIGSCR-664 | To check the " Footer " Design . |  | <click> <slide> | Design should be as per Figma. | In Product Ev car Insurance and Ev bike Insurance list is Missing | FAIL | RAVI | 2023-09-27 | NOVDIGSCR-734 |  | RAVI

## Componet Test Case
Test Case Basic Information
Project Name : | NOVA-DIGITAL-SCRUM
Screen Name : | FW EV NEW LANING PAGE
Pre Requisite : | New FW Landing Page for EV Vehicle | [6 empty] | Testing Type : | System Integration Testing
Instructions : | [8 empty] | Cycle 1
Testcase ID | Step No. | Sprint Number | User Story | Input Specification | Help / Remarks | Input/Test Data | Expected Result | Actual Result | (Pass/Fail) | Tested By | Tested Date : | Defect Id
TS-FW-EV_001 : To check all the Components in FW EV New Landing Page.
TC-C_FW-EV_001 | TC-C_FW-EV_001_01 | 6 | NOVDIGSCR-664 | To Verify the field " Car Reg Num " with invalid input as Null input. |  | --Select-- | System should not accept the provided invalid data in the field " Car Reg Num ". It should throw an error message as "Enter valid Car registration number" | System is not accept the provided invalid data in the field " Car Reg Num ". It is throw an error message as "Enter valid Car registration number" | Pass | RAVI | 2023-09-27
TC-C_FW-EV_001 | TC-C_FW-EV_001_02 | 6 | NOVDIGSCR-664 | To Verify the field " Car Reg Num " with invalid input as Only Numbers. |  | 3663 | It should throw an error message as "Enter valid Car registration number" | System is not accept the provided invalid data in the field " Car Reg Num ". It is throw an error message as "Enter valid Car registration number" | Pass | RAVI | 2023-09-27
TC-C_FW-EV_001 | TC-C_FW-EV_001_03 | 6 | NOVDIGSCR-664 | To Verify the field " Car Reg Num " with invalid input as Only alphabets. |  | TNADFG | It should throw an error message as "Enter valid Car registration number" | System is not accept the provided invalid data in the field " Car Reg Num ". It is throw an error message as "Enter valid Car registration number" | Pass | RAVI | 2023-09-27
TC-C_FW-EV_001 | TC-C_FW-EV_001_04 | 6 | NOVDIGSCR-664 | To Verify the field " Car Reg Num " with invalid input as Special Charactors. |  | TN@CH123# | It should throw an error message as "Enter valid Car registration number" | System is not accept the provided invalid data in the field " Car Reg Num ". It is throw an error message as "Enter valid Car registration number" | Pass | RAVI | 2023-09-27
TC-C_FW-EV_001 | TC-C_FW-EV_001_05 | 6 | NOVDIGSCR-664 | To check what if first 2 character of the field is not alphabets |  | 22cg3443 | It should throw an error message as "Enter valid Car registration number" | System is not accept the provided invalid data in the field " Car Reg Num ". It is throw an error message as "Enter valid Car registration number" | Pass | RAVI | 2023-09-27
TC-C_FW-EV_001 | TC-C_FW-EV_001_06 | 6 | NOVDIGSCR-664 | To check what if 3rd,4th character of the car registration number field is not numeric. |  | TNB3232 | It should throw an error message as "Enter valid Car registration number" | System is not accept the provided invalid data in the field " Car Reg Num ". It is throw an error message as "Enter valid Car registration number" | Pass | RAVI | 2023-09-27
TC-C_FW-EV_001 | TC-C_FW-EV_001_07 | 6 | NOVDIGSCR-664 | To check what happens if 5th character of the car registration number field will be either alphabet or numeric. |  | TN02J2343, TN02243 | It should throw an error message as "Enter valid Car registration number" | System is not accept the provided invalid data in the field " Car Reg Num ". It is throw an error message as "Enter valid Car registration number" | Pass | RAVI | 2023-09-27
TC-C_FW-EV_001 | TC-C_FW-EV_001_08 | 6 | NOVDIGSCR-664 | To check what if 5th, 6th character of the car registration number field is not alphabets. |  | TN02J2343, TN02243 | It should throw an error message as "Enter valid Car registration number" | System is not accept the provided invalid data in the field " Car Reg Num ". It is throw an error message as "Enter valid Car registration number" | Pass | RAVI | 2023-09-27
TC-C_FW-EV_001 | TC-C_FW-EV_001_09 | 6 | NOVDIGSCR-664 | To check what if 7th,8th,9th,10th character of the car registration field is not numeric. |  | TN01THQWER | It should throw an error message as "Enter valid Car registration number" | System is not accept the provided invalid data in the field " Car Reg Num ". It is throw an error message as "Enter valid Car registration number" | Pass | RAVI | 2023-09-27
TC-C_FW-EV_001 | TC-C_FW-EV_001_10 | 6 | NOVDIGSCR-664 | To Verify the field "Mobile No." with valid data Starting with 9. |  | 9962557169 | System should accept the provided valid data in the field "Mobile No.". | System is accepting the provided valid data in the field "Mobile No.". | Pass | RAVI | 2023-09-27
TC-C_FW-EV_001 | TC-C_FW-EV_001_11 | 6 | NOVDIGSCR-664 | To Verify the field "Mobile No." with valid data Starting with 8. |  | 8775813169 | System should accept the provided valid data in the field "Mobile No.". | System is accepting the provided valid data in the field "Mobile No.". | Pass | RAVI | 2023-09-27
TC-C_FW-EV_001 | TC-C_FW-EV_001_12 | 6 | NOVDIGSCR-664 | To Verify the field "Mobile No." with valid data Starting with 7. |  | 7810006174 | System should accept the provided valid data in the field "Mobile No.". | System is accepting the provided valid data in the field "Mobile No.". | Pass | RAVI | 2023-09-27
TC-C_FW-EV_001 | TC-C_FW-EV_001_13 | 6 | NOVDIGSCR-664 | To Verify the field "Mobile No." with valid data Starting with 6. |  | 6317327320 | System should accept the provided valid data in the field "Mobile No.". | System is accepting the provided valid data in the field "Mobile No.". | Pass | RAVI | 2023-09-27
TC-C_FW-EV_001 | TC-C_FW-EV_001_14 | 6 | NOVDIGSCR-664 | To Verify the field "Mobile No." with invalid data Starting with 2. |  | 2345678932 | System should not accept the provided invalid data in the field "Mobile No.". | System is not accept the provided invalid data in the field "Mobile No.". | Pass | RAVI | 2023-09-27
TC-C_FW-EV_001 | TC-C_FW-EV_001_15 | 6 | NOVDIGSCR-664 | To Verify the field "Mobile No." with invalid data Starting with 3. |  | 3987654321 | System should not accept the provided invalid data in the field "Mobile No.". | System is not accept the provided invalid data in the field "Mobile No.". | Pass | RAVI | 2023-09-27
TC-C_FW-EV_001 | TC-C_FW-EV_001_16 | 6 | NOVDIGSCR-664 | To Verify the field "Mobile No." with invalid data Starting with 4. |  | 4789653218 | System should not accept the provided invalid data in the field "Mobile No.". | System is not accept the provided invalid data in the field "Mobile No.". | Pass | RAVI | 2023-09-27
TC-C_FW-EV_001 | TC-C_FW-EV_001_17 | 6 | NOVDIGSCR-664 | To Verify the field "Mobile No." with invalid data Starting with 5. |  | 5863214563 | System should not accept the provided invalid data in the field "Mobile No.". | System is not accept the provided invalid data in the field "Mobile No.". | Pass | RAVI | 2023-09-27
TC-C_FW-EV_001 | TC-C_FW-EV_001_18 | 6 | NOVDIGSCR-664 | To Verify the field "Mobile No." with invalid data - Empty field. |  |  | System should not accept the provided invalid data in the field "Mobile No.". | System is not accept the provided invalid data in the field "Mobile No.". | Pass | RAVI | 2023-09-27
TC-C_FW-EV_001 | TC-C_FW-EV_001_19 | 6 | NOVDIGSCR-664 | To Verify the field "Mobile No." with invalid data - Space between numbers. |  | 9876 3210 | System should not accept the provided invalid data in the field "Mobile No.". | System is not accept the provided invalid data in the field "Mobile No.". | Pass | RAVI | 2023-09-27
TC-C_FW-EV_001 | TC-C_FW-EV_001_20 | 6 | NOVDIGSCR-664 | To Verify the field "Mobile No." with invalid data - All values are Zeros. |  | 0 | System should not accept the provided invalid data in the field "Mobile No.". | System is not accept the provided invalid data in the field "Mobile No.". | Pass | RAVI | 2023-09-27
TC-C_FW-EV_001 | TC-C_FW-EV_001_21 | 6 | NOVDIGSCR-664 | To Verify the field "Mobile No." with invalid data - With Alpha numeric value. |  | ABC123 | System should not accept the provided invalid data in the field "Mobile No.". | System is not accept the provided invalid data in the field "Mobile No.". | Pass | RAVI | 2023-09-27
TC-C_FW-EV_001 | TC-C_FW-EV_001_22 | 6 | NOVDIGSCR-664 | To Verify the field "Mobile No." with invalid data - With special Characters. |  | 98764@#$@#$@ | System should not accept the provided invalid data in the field "Mobile No.". | System is not accept the provided invalid data in the field "Mobile No.". | Pass | RAVI | 2023-09-27
TC-C_FW-EV_001 | TC-C_FW-EV_001_23 | 6 | NOVDIGSCR-664 | To Verify the field "Mobile No." with maximum numbers. - More than 10 numbers. |  | 9880000000000 | System should not accept the provided invalid data in the field "Mobile No.". | System is not accept the provided invalid data in the field "Mobile No.". | Pass | RAVI | 2023-09-27
TC-C_FW-EV_001 | TC-C_FW-EV_001_24 | 6 | NOVDIGSCR-664 | To Verify the field "Mobile No." with Duplicate Values. |  | 9962557169 | System should not accept the provided invalid data in the field "Mobile No.". | System is not accept the provided invalid data in the field "Mobile No.". | Pass | RAVI | 2023-09-27