## Sprint28-Capacity
Sprint Capacity Plan
Project | NOVA-DIG Sprint 13
Sprint Duration (In Days) | 10 | Start Date | 2024-01-01 | End Date | 2024-01-15
Resource Capacity
Res.Name | Capacity (Hrs) | Contribution % | Non Availability (Hrs) | Available Capacity
Saravanan P | 80 | 40 |  | 32
Surender | 80 | 55 |  | 44
Balaji Kannan | 80 | 60 |  | 48
Sivashankaran | 80 | 80 |  | 64
Pradeep | 80 | 65 |  | 52
Raviraj | 80 | 50 |  | 40
Total Capacity |  |  | 0 | 280
Plan Overview
Estimated Task Total Hrs | Load % | Team Velocity | Story Points Committed
277.8 | 99.2143 | 24 | 6

## Sprint28-StorySizing
Story Sizing
Story Sizing
User Story No | Saravanan P | Surender | Balaji | Sivasankaran | Pradeep | Ravi | Finalized S.P | Efforts
NOVDIGSCR-1891 | [6 empty] | 3 | 20
NOVDIGSCR-1858 | [6 empty] | 3 | 20
NOVDIGSCR-1902 | [6 empty] | 8 | 80
NOVDIGSCR-1847 | [6 empty] | 5 | 40
NOVDIGSCR-1880 | [6 empty] | 8 | 80
NOVDIGSCR-1869 | [6 empty] | 5 | 40
Total | [6 empty] | 32 | 280
Reference:
NC | Not Able to Contribute
Finalized S.P | Finalized Story Points
Sizing | Man Hrs
1 | <=8
2 | <=16
3 | <=24
5 | <=40
8 | <=80

## Sheet3 (hidden)
Story Point | Sum of Hours
(empty) | 105
5 | 6
8 | 9
Total Result | 120

## Sprint28-Task Estimation
WBS | [9 empty] | 40 | 10 | 15 | 35
[10 empty] | Coding | Design | Unit Testing | Testing | Total Efforts
[9 empty] | 1 | 16 | 4 | 6 | 14 | 40
[9 empty] | 2 | 16 | 4 | 6 | 14 | 40
[9 empty] | 3 | 32 | 8 | 12 | 28 | 80
[9 empty] | 4 | 16 | 4 | 6 | 14 | 40
[9 empty] | 5 | 16 | 4 | 6 | 14 | 40
[9 empty] | 6 | 24 | 6 | 9 | 21 | 60
[9 empty] | 7 | 0 | 0 | 0 | 0
8
9
Sno | UserStory | Story Description | SubTask |  | Activity | Hours | Resource | Story Point | [6 empty] | Resource
1 | NOVDIGSCR-2705 | Policy generation on CRON | Design | 4 | Design Work |  | Ijas | [6 empty] | 300 | Manikandan
[5 empty] | Design Review |  | Muthu | [7 empty] | MuthulakshmiA
|  |  | Coding | 16 | UI Changes |  | Ijas
API Changes
[5 empty] | Code Changes |  | Ijas | [7 empty] | Sivasankaran
[5 empty] | Code Review |  | Muthu | [7 empty] | Saravanan P | Manikandan
|  |  | Unit Test | 6 | Unit test case Preparation |  | Ijas | [7 empty] | Pradeep | Sivasankaran
[5 empty] | Unit test case review |  | Muthu | [7 empty] | Saravanan P | MuthulakshmiA
[5 empty] | Unit test execution |  | Ijas | [7 empty] | Pradeep | KapilDev
|  |  | Testing | 14 | Test Case Prepartion |  | Ravi | [7 empty] | Pradeep | Nihal shameem
[5 empty] | Test Case Review |  | Muthu | [7 empty] | Saravana Muthu T | Surendran KU
[5 empty] | Test Execution |  | Ravi | [7 empty] | Pradeep | Raviraj
2 | NOVDIGSCR-2717 | CMS Optimization on view logs | Design | 4 | Design Work |  | Ijas | [7 empty] | Manikandan
[5 empty] | Design Review |  | Muthu | [7 empty] | MuthulakshmiA
|  |  | Coding | 16 | UI Changes |  | Ijas
API Changes
[5 empty] | Code Changes |  | Ijas | [7 empty] | Sivachandran
[5 empty] | Code Review |  | Muthu | [7 empty] | Saravanan P
|  |  | Unit Test | 6 | Unit test case Preparation |  | Ijas | [7 empty] | Pradeep
[5 empty] | Unit test case review |  | Muthu | [7 empty] | MuthulakshmiA
[5 empty] | Unit test execution |  | Ijas | [7 empty] | Pradeep
|  |  | Testing | 14 | Test Case Prepartion |  | Ravi | [7 empty] | Pradeep
[5 empty] | Test Case Review |  | Muthu | [7 empty] | Saravana Muthu T
[5 empty] | Test Execution |  | Ravi | [7 empty] | Pradeep
3 | NOVDIGSCR-2728 | Digilocker for Motor aid and GCCV, PCCV | Design | 8 | Design Work |  | Thufail | [7 empty] | Manikandan | Pradeep
[5 empty] | Design Review |  | Muthu | [7 empty] | MuthulakshmiA | Balaji Kannan
|  |  | Coding | 32 | UI Changes |  | Thufail
API Changes
[5 empty] | Code Changes |  | Thufail | [7 empty] | Nihal | Saravanan P
[5 empty] | Code Review |  | Muthu | [7 empty] | Saravanan P
|  |  | Unit Test | 12 | Unit test case Preparation |  | Thufail | [7 empty] | Raviraj
[5 empty] | Unit test case review |  | Muthu | [7 empty] | Saravanan P
[5 empty] | Unit test execution |  | Thufail | [7 empty] | Raviraj
|  |  | Testing | 28 | Test Case Prepartion |  | Ravi | [7 empty] | Raviraj
[5 empty] | Test Case Review |  | Muthu | [7 empty] | Saravana Muthu T
[5 empty] | Test Execution |  | Ravi | ` | [6 empty] | Raviraj
4 | NOVDIGSCR-2740 | Add policy generation feature on Assist car and renewals | Design | 4 | Design Work |  | Balaji
[5 empty] | Design Review |  | Muthu
|  |  | Coding | 16 | UI Changes |  | Balaji
API Changes
[5 empty] | Code Changes |  | Balaji
[5 empty] | Code Review |  | Muthu
|  |  | Unit Test | 6 | Unit test case Preparation |  | Balaji
[5 empty] | Unit test case review |  | Muthu
[5 empty] | Unit test execution |  | Balaji
|  |  | Testing | 14 | Test Case Prepartion |  | Ravi
[5 empty] | Test Case Review |  | Muthu
[5 empty] | Test Execution |  | Ravi
5 | NOVDIGSCR-2762 | Hospital Daily cash changes on nominee details | Design | 4 | Design Work |  | Ijas
[5 empty] | Design Review |  | Muthu
|  |  | Coding | 16 | UI Changes |  | Balaji
API Changes
[5 empty] | Code Changes |  | Balaji
[5 empty] | Code Review |  | Muthu
|  |  | Unit Test | 6 | Unit test case Preparation |  | Balaji
[5 empty] | Unit test case review |  | Muthu
[5 empty] | Unit test execution |  | Balaji
|  |  | Testing | 14 | Test Case Prepartion |  | Pradeep
[5 empty] | Test Case Review |  | Muthu
[5 empty] | Test Execution |  | Pradeep
6 | NOVDIGSCR-2751 | Issues in ASHA renewal journey | Design | 6 | Design Work |  | Ijas
[5 empty] | Design Review |  | Muthu
|  |  | Coding | 24 | UI Changes |  | Ijas
API Changes
[5 empty] | Code Changes |  | Ijas
[5 empty] | Code Review |  | Muthu
|  |  | Unit Test | 9 | Unit test case Preparation |  | Ijas
[5 empty] | Unit test case review |  | Muthu
[5 empty] | Unit test execution |  | Ijas
|  |  | Testing | 21 | Test Case Prepartion |  | Pradeep
[5 empty] | Test Case Review |  | Muthu
[5 empty] | Test Execution |  | Pradeep

## Contribution
Total Hrs |  | 80
|  | Efforts | Percentage
| BalajiKannan |  | 0
| Manikandan |  | 0
| Muthulakshmi |  | 0 | 400
| Nihal |  | 0
| Saravanan P |  | 0
| Sivashankaran |  | 0
| Surender |  | 0
| Thufail |  | 0
| Mydeen Ijas |  | 0
| Mohan |  | 0
| Kapil |  | 0
| Saravana muthu |  | 0
| Pradeep |  | 0
| Ravi |  | 0