## Deafect Tracker
Defect Tracker
DEFECT TRACKER
Project ID/Name:
Defect ID | Defect ID | Defect Logged Date | Defect logged in Sprint | Defect From | Package No. / Build Reference | Package/ Build Release Date | Requirement ID | Module | Feature / Screen | Defect Description | Screen Shots Attached | Defect Classification | Sub classification | Defect Severity | Status | Raised By | Fixed by | Fixed Date | Defect Closed Date | Defect closed in Sprint | Remarks
NOVDIGSCR-1837 | Stage | 2024-03-08 | 17 | Website |  | 2024-03-08 | NOVDIGSCR-1606 | ABHA card creation through SGI website Design | ABHA PAGE | Send OTP, verify OTP, Create ABHA ID,Download ABHA ID, button alignment Mismatching with this resolution.(768*1024) NOVDIGSCR-1837 |  | Alignment | Button Alignment |  | Closed | Pradeep Kumar |  |  | 2024-03-09
NOVDIGSCR-1838 | Stage | 2024-03-08 | 17 | Website |  | 2024-03-08 | NOVDIGSCR-1606 | ABHA card creation through SGI website Design | ABHA PAGE | Steper content is Not showing in all page with this resolution. (600*960) NOVDIGSCR-1838 |  | Content | Content Missing |  | Closed | Pradeep Kumar |  |  | 2024-03-09
NOVDIGSCR-1839 | Stage | 2024-03-08 | 17 | Website |  | 2024-03-08 | NOVDIGSCR-1606 | ABHA card creation through SGI website Design | ABHA PAGE | The final ABHA card QR code and mobile number alignment issue. (991*540) NOVDIGSCR-1839 |  | Alignment | Content Alignment |  | Closed | Pradeep Kumar |  |  | 2024-03-09
Note on A6: SEPG: Defect Id format: First two characters of project name(ER) +Defect no.(D001) e.g ERD001 , ERD002, ERD003…ERD034 etc..
Note on F6: SEPG: Fill NA if the Defect type is Unit Testing
Note on G6: SEPG: Fill NA if the Defect type is Unit Testing