## Defect Tracker
Defect Tracker
DEFECT TRACKER
Customization ID/Name:
Defect ID | Defect Type | Defect Logged Date | Defect from | Package No. / Build Reference | Package/ Build Release Date | Requirement ID | Module | Feature / Screen | Defect Description | Screen Shots Attached | Defect Classification | Sub classification | Defect Severity | Status | Raised By | Fixed by | Fixed Date | Defect Closed Date | Remarks
SGIP00001 | SIT | 2025-07-18 | Application |  | 2025-07-18 | NOVAPHILCM-154 |  | Mis Report | Status not Update as fully paid , even it fully paid in RI screen. |  | Functional | Requirements |  | Closed | Ravi | Venkatalakshmi | 2025-07-28 | 2025-07-28 | NOVAPHILCM-1281
SGIP00002 | SIT | 2025-07-21 | Application |  | 2025-07-21 | NOVAPHILCM-154 |  | Mis Report | Multiple RI insurers are not printing in Report. |  | Functional | Requirements |  | Closed | Ravi | Venkatalakshmi | 2025-08-28 | 2025-08-28 | NOVAPHILCM-1282
SGIP00003 | SIT | 2025-07-21 | Application |  | 2025-07-21 | NOVAPHILCM-154 |  | Mis Report | Fully RI Paid leads also printing as Partially Paid. |  | Functional | Requirements |  | Closed | Ravi | Venkatalakshmi | 2025-07-28 | 2025-07-28 | NOVAPHILCM-1283
SGIP00004 | SIT | 2025-07-21 | Application |  | 2025-07-21 | NOVAPHILCM-154 |  | Mis Report | Rate wrongly calculating |  | Functional | Requirements |  | Closed | Ravi | Venkatalakshmi | 2025-07-28 | 2025-07-28 | NOVAPHILCM-1284
SGIP00005 | SIT | 2025-07-21 | Application |  | 2025-07-21 | NOVAPHILCM-154 |  | Mis Report | No.of installment Wrongly calculating |  | Functional | Requirements |  | Closed | Ravi | Venkatalakshmi | 2025-08-28 | 2025-08-28 | NOVAPHILCM-1285
SGIP00006 | SIT | 2025-07-21 | Application |  | 2025-07-21 | NOVAPHILCM-154 |  | Mis Report | RI net premium wrongly calculating, WHT is missing . |  | Functional | Requirements |  | Closed | Ravi | Venkatalakshmi | 2025-07-28 | 2025-07-28 | NOVAPHILCM-1286
SGIP00007 | SIT | 2025-07-21 | Application |  | 2025-07-21 | NOVAPHILCM-154 |  | Mis Report | LRI Share wrongly calculating |  | Functional | Requirements |  | Closed | Ravi | Venkatalakshmi | 2025-07-28 | 2025-07-28 | NOVAPHILCM-1287
SGIP00008 | SIT | 2025-07-21 | Application |  | 2025-07-21 | NOVAPHILCM-154 |  | Mis Report | Line, subline, BussinessType Filter not working |  | Functional | Requirements |  | Closed | Ravi | Venkatalakshmi | 2025-08-28 | 2025-08-28 | NOVAPHILCM-1288
SGIP00009 | SIT | 2025-07-24 | Application |  | 2025-07-21 | NOVAPHILCM-154 |  | Mis Report | Co-insurance - sgi share wrongly calculating, rate, Lri % on sgi share CBPW date, ow ppw date, Payment date, OS beyond ppw date wrongly calculating Agent Direct commission not print for CGL Leads |  | Functional | Requirements |  | Closed | Ravi | Venkatalakshmi | 2025-08-28 | 2025-08-28 | NOVAPHILCM-1293
SGIP00010 | SIT | 2025-07-25 | Application |  | 2025-07-21 | NOVAPHILCM-154 |  | Mis Report | Motor leads not printing |  | Functional | Requirements |  | Closed | Ravi | Venkatalakshmi | 2025-08-28 | 2025-08-28 | NOVAPHILCM-1294
SGIP00011 | SIT | 2025-07-25 | Application |  | 2025-07-21 | NOVAPHILCM-154 |  | Mis Report | CGL Agent commission not print in report |  | Functional | Requirements |  | Closed | Ravi | Venkatalakshmi | 2025-08-29 | 2025-08-29 | NOVAPHILCM-1296
Note on A6: SEPG: Defect Id format: First two characters of project name(ER) +Defect no.(D001) e.g ERD001 , ERD002, ERD003…ERD034 etc..
Note on B6: SEPG: Select the Defect Type from the Drop Down List
Note on E6: SEPG: Fill NA if the Defect type is Unit Testing
Note on F6: SEPG: Fill NA if the Defect type is Unit Testing

## Defect Status
Defect Status Summary Report
| SI. No | Defect ID | Status | Open | 0
| 1 | SGIP00001 | Closed | Fixed | 0
| 2 | SGIP00002 | Closed | Re-Open | 0
| 3 | SGIP00003 | Closed | Deferred | 0
| 4 | SGIP00004 | Closed | Closed | 11
| 5 | SGIP00005 | Closed | Total | 11
| 6 | SGIP00006 | Closed
| 7 | SGIP00007 | Closed
| 8 | SGIP00008 | Closed
| 9 | SGIP00009 | Closed
| 10 | SGIP00010 | Closed
| 11 | SGIP00011 | Closed

## Guidelines
Guidelines for using this Document
Defect Report
Defect ID | Provide the Defect ID in this column. The naming convention for a defect ID is as follows: First four characters of Customization name +Last five are incremental numbers Ex:STFC00001
Defect type | Unit testing or SI testing
Defect Logged Date | Date in dd-mmm-yyyy format in which the defect was logged in the tracker. In ideal scenario this date should be same as the date in which the defect was identified.
Defect from | The way in which the "Defect" can be identified. Package/Build: "Defects" found after executing the Package/build. Application: "Defects' identified while doing the regression testing/adhoc testing on application Unit:"Defects" identified from unit testing
Package No. / Build Reference | Unique ID number which is maintained by the development team while releasing the Package/Build to testing team. Fill NA if it is a unit testing defect
Package / Build Release Date | Date in dd-mmm-yyyy format in which the Package/Build released by development team to testing Fill NA if it is a unit testing defect
Requirement ID | Requirement ID: Unique ID number which is maintained by the BCG /Client while preparing the Change Request document or Issues respectively.
Module | Module Name of the project For Ex:- System Administration,Investments,Leding,General Accounting etc.
Feature/Screen | Mention the "Screen Path" in which the "Defect" exists in. This should be the URL of the page where the defect could be identified Example: Lending>>General>>Masters>>Customer Information>>Martial Status Mention the name of the Screen in which the Defect is identified Example: Marital Status
Defect Description | Describe in brief about the identified defect. If possible we can also mention the way in which the "Defect" can be identified.
Defect Classification | Categorize the Defect in any one of the following category. This activity needs to be populated by the Testing Team Functional: Any defect that does not meet the requirement Non-Functional: Any defect that does not meet the system aspects Development Issues: Any defects that does not meet technical aspects Data: Defects related to "Data". This may be improper data, wrong calculation or wrong fetching etc. Infrastructure: The defect due to environmental changes
Sub classification | Select the sub classification of the defect based on the defect type and defect classification 1 Non Functional a) Security b) Performance (Load Testing & Stress Testing) c) UI Issue (includes Usability, Cosmetic, Screen Alignment and Compatibility) d) Time Issue 2 Development Issues a) Syntax Error b) Spelling Mistake (Typo) c) Unhandled Error (includes No Exception Handling) 3 Functional a) Business Logic b) Business Flow c) Missing Validation (Data validation) d) Computational e) Requirements (Missing and Incorrect) 4 Data a) Data Integrity 5 Infrastructure a) Environmental
Defect Severity | Mention the Defect "Severity" here. There are 3 severity types
Severity (Critical) Criteria
Business Logic
Business Flow
Functions not as per Requirement
Validation Missing
System Inoperable
System Hanging
Cmd Button not working
Severity (Major) Criteria
Module/Feature inoperable
Load Performance
Data Truncation or Getting corrupted
Component not working properly
Functionality Not implemented properly
UI Disturbance
Required feature is not handled in SRS
Severity (Minor) Criteria
Module/Feature Not Working as required
Will not affect Daily Business
Not a show stopper
There will be a reasonable workaround
Cosmetic Issue
Cosmetic defects with user interface
Status | Status of the Defect has to be updated here from the list of values provided. Open: When the defect has been logged in the tracker for the first time Fixed: When the defect has been addressed by the developer Reopen, Reopen 1`, Reopen 2, Reopen 3: If any fixed or closed defect are resurfacing (due to changes in some other requirement), then status will be updated until the defect is fixed and closed completely Deferred: When the defect identified by the Tester, but the Client does not want it to be addressed in this release or want to defer the fix to a later time Closed: When the defect has been verified for the fix and the fix is fine
Raised By | Mention the name of the person who identified the Defect. This should typically be the same person who logs the defect
Fixed by | Name of the person who has fixed the defect
Defect Closed Date | Date in dd/mm/yyyy format in which the defect was finally closed (verified by the Testing Team)
Remarks | This column can be used to add any free text with respect to a defect.