## Revision History
Sprint Plan
Revision History
Version No | Date | Reason For Changes | Author | Reviewer | Approver
0.01 | 2024-09-13 | Draft | Saravana kumar M
0.02 | 2024-09-16 | Reviewed | Saravana kumar M | Sankar Ganesh
1 | 2024-09-16 | Baselined | Saravana kumar M | Sankar Ganesh | Sankar Ganesh
Sheet 17 of 17

## Sprint Backlog
Sprint Backlog
Project Name/ID | NOVPHILSCR | Scrum Team ID | NOVPHILSCR | Product Owner | NIJANTHAN PL | Sprint Goal
Project Manager | SANKAR GANESH | Sprint No | 36 | Scrum Master | SARAVANA KUMAR M | Need to complete all the taken user stories and deployed in live on time.
S.No | User Story ID | Priority | Size Estimation for User Story (Storypoints) | Dependencies | Definition of Done (DoD) | Tasks | Resource Name | Planned Effort (in Hrs) | Actual Effort (in Hrs) Day 1 | Actual Effort (in Hrs) Day 2 | Actual Effort (in Hrs) Day 3 | Actual Effort (in Hrs) Day 4 | Actual Effort (in Hrs) Day 5 | Actual Effort (in Hrs) Day 6 | Actual Effort (in Hrs) Day 7 | Actual Effort (in Hrs) Day 8 | Actual Effort (in Hrs) Day 9 | Actual Effort (in Hrs) Day 10
1 | NOVPHILSCR-1994 | High | 8 |  |  | Design | MUTHURAJA | 8 | 7 | 1
[6 empty] | Design Review | DHANALAKSHMI | 2
[6 empty] | Coding | MUTHURAJA | 12 |  | 7 | 5
[6 empty] | Code Review | DHANALAKSHMI | 1
[6 empty] | Unit Test Preparation | MUTHURAJA | 5 |  |  | 2.5 | 2.5
[6 empty] | Unit Test Review | DHANALAKSHMI | 1
[6 empty] | Unit Testing | MUTHURAJA | 5 |  |  |  | 5
[6 empty] | Test Case & Scenario Preparation | ANURAG KUMAR | 6 |  |  |  |  | 6
[6 empty] | Test Case Review | DHANALAKSHMI | 3
[6 empty] | Test Execution | ANURAG KUMAR | 8 | [8 empty] | 4 | 3
2 | NOVPHILSCR-2027 | High | 8 |  |  | Design | VENKATALAKSHMI | 8 | 3 | 3 | 2
[6 empty] | Design Review | DHANALAKSHMI | 2
[6 empty] | Coding | VENKATALAKSHMI | 12 | 4.5 | 4.5 | 3
[6 empty] | Code Review | DHANALAKSHMI | 1
[6 empty] | Unit Test Preparation | VENKATALAKSHMI | 5 |  |  | 2.5 |  |  |  | 2.5
[6 empty] | Unit Test Review | DHANALAKSHMI | 1
[6 empty] | Unit Testing | VENKATALAKSHMI | 5 |  |  |  | 2.5 | 2.5
[6 empty] | Test Case & Scenario Preparation | VINOTHINI | 6
[6 empty] | Test Case Review | DHANALAKSHMI | 3
[6 empty] | Test Execution | VINOTHINI | 7
3 | NOVPHILSCR-2104 | High | 8 |  |  | Design | NAGE GOWDA | 8 | 3 | 3 | 2
[6 empty] | Design Review | DHANALAKSHMI | 1
[6 empty] | Coding | NAGE GOWDA | 12 | 4 | 4 | 4
[6 empty] | Code Review | DHANALAKSHMI | 1
[6 empty] | Unit Test Preparation | NAGE GOWDA | 5 | [5 empty] | 5
[6 empty] | Unit Test Review | DHANALAKSHMI | 1
[6 empty] | Unit Testing | NAGE GOWDA | 5 | [6 empty] | 5
[6 empty] | Test Case & Scenario Preparation | RAVI RAJ | 8 | 3 | 2.5 | 2.5
[6 empty] | Test Case Review | DHANALAKSHMI | 2
[6 empty] | Test Execution | RAVI RAJ | 8 | [6 empty] | 3.5 | 4.5
4 | NOVPHILSCR-2005 | Medium | 5 |  |  | Design | MUTHURAJA | 8 |  |  |  |  | 8
[6 empty] | Design Review | DHANALAKSHMI | 1
[6 empty] | Coding | MUTHURAJA | 8 | [5 empty] | 8
[6 empty] | Code Review | DHANALAKSHMI | 1
[6 empty] | Unit Test Preparation | MUTHURAJA | 3 | [6 empty] | 3
[6 empty] | Unit Test Review | DHANALAKSHMI | 1
[6 empty] | Unit Testing | MUTHURAJA | 3 | [6 empty] | 2 | 1
[6 empty] | Test Case & Scenario Preparation | VINOTHINI | 6 |  | 4 | 2
[6 empty] | Test Case Review | DHANALAKSHMI | 2
[6 empty] | Test Execution | VINOTHINI | 8 | [8 empty] | 8
5 | NOVPHILSCR-2168 | Medium | 5 |  |  | Design | VENKATALAKSHMI | 8 | 3.5 | 3.5 | 1
[6 empty] | Design Review | DHANALAKSHMI | 1 |  | 4.5
[6 empty] | Coding | VENKATALAKSHMI | 12 |  | 4.5 | 4.5 | 3
[6 empty] | Code Review | DHANALAKSHMI | 1
[6 empty] | Unit Test Preparation | VENKATALAKSHMI | 5 | [5 empty] | 2.5 | 2.5
[6 empty] | Unit Test Review | DHANALAKSHMI | 1
[6 empty] | Unit Testing | VENKATALAKSHMI | 5 | [6 empty] | 2.5 | 2.5
[6 empty] | Test Case & Scenario Preparation | VINOTHINI | 6 |  |  |  | 6
[6 empty] | Test Case Review | DHANALAKSHMI | 1
[6 empty] | Test Execution | VINOTHINI | 7 | [5 empty] | 7
6 |  | Medium | 5 |  |  | Design | MUTHURAJA | 8 | [6 empty] | 3 | 4 | 1
[6 empty] | Design Review | DHANALAKSHMI | 1
[6 empty] | Coding | MUTHURAJA | 8 | [7 empty] | 3 | 3 | 2
[6 empty] | Code Review | DHANALAKSHMI | 1
[6 empty] | Unit Test Preparation | MUTHURAJA | 3 | [8 empty] | 3
[6 empty] | Unit Test Review | DHANALAKSHMI | 1
[6 empty] | Unit Testing | MUTHURAJA | 3 | [9 empty] | 3
[6 empty] | Test Case & Scenario Preparation | ANURAG KUMAR | 8 | [6 empty] | 4 | 4
[6 empty] | Test Case Review | DHANALAKSHMI | 1
[6 empty] | Test Execution | ANURAG KUMAR | 8 | [8 empty] | 4 | 4
Total |  |  | 39 |  |  |  |  | 282 | 28 | 41.5 | 31 | 19 | 16.5 | 22.5 | 28 | 19 | 23 | 12
Note on E7: Admin: Dependencies on people, support group etc.

## Sprint Capacity Plan
Sprint Capacity Plan
Sprint Duration (In Days) | 10 | Start Date | 2024-09-16 | End Date | 2024-09-30 | Sprint Review & Retro Date | 2024-09-30
Capacity (in Hours)
Resource Name | Planned Leave (in Hours) | Per Day (in Hours) | Sprint (Per Resource in Hours) | Available capacity(in Hrs) | Task Planned (in Hrs) | Available (in Hrs) | Load %
MUTHURAJA |  | 8 | 80 | 80 | 74 | 6 | 92.5
NAGE GOWDA |  | 8 | 80 | 80 | 30 | 50 | 37.5
VENKATALAKSHMI |  | 8 | 80 | 80 | 60 | 20 | 75
VINOTHINI |  | 4 | 40 | 40 | 40 | 0 | 100
ANURAG KUMAR |  | 4 | 40 | 40 | 32 | 8 | 80
DHANALAKSHMI | 8 | 4 | 40 | 32 | 32 | 0 | 100
RAVI RAJ |  | 4 | 40 | 40 | 16 | 24 | 40
|  |  | 400 | 392 | 284 | 108 | 75
Note on B5: SEPG: Manual Entry field

## Sprint Burndown chart
Sprint Burndown chart
Sprint BurnDown chart : Day Wise Data
Sprint Burn down Data
| Day | Total Planned Hours | Capacity (in Hours) | Actual Effort Burnt | Actual Hours
| Day 0 | 282
| Day 1 | 242 | 40 | 254 | 28
| Day 2 | 202 | 40 | 212.5 | 41.5
| Day 3 | 162 | 40 | 181.5 | 31
| Day 4 | 122 | 40 | 162.5 | 19
| Day 5 | 82 | 40 | 146 | 16.5
| Day 6 | 42 | 40 | 123.5 | 22.5
| Day 7 | 2 | 40 | 95.5 | 28
| Day 8 | -38 | 40 | 76.5 | 19
| Day 9 | -78 | 40 | 53.5 | 23
| Day 10 | -118 | 40 | 41.5 | 12
Sprint BurnDown Chart
It is metric that compares actual and expected progress and shows whether the team is ahead or behind the expectations. ( Provide inference based on the chart)