## Sheet1
S.No | Issues description | Status | DevStatus | TestStatus | TestStatus
1 | Recommendation dropdown is empty | Open | fixed | closed | closed
2 | Declared Value should allow only 2 decimal. | Open | fixed | closed | closed
3 | While adding material damage SI is freeze and autofeatching from SMIs but in edit it is allowing to change the SI | Open | fixed | closed | closed
4 | system is not allowing to enter the Special character in Data Media Details & Increase in Cost of Workers only allows "&" | Open | fixed | closed | closed
5 | While downloading the Inventory Upload Excel File Template system display file path is empty. | Open |  |  | closed
6 | Once proposal is converted Data Media Details & Increase in Cost of Workers Item Description is getting refresh. | Open | fixed | closed | closed
7 | In SMI grid calculated premium is displaying 0 | Open | ignore
8 | Section 1 and section 2 is select but without selecting basic cover system allow to generate the policy. | Open | fixed | closed | closed
9 | Clause wording not displaying in PDF 10000/46/24/000001 | Open
10 | Policy schedule is not displaying properly. 10000/46/24/000002 | Open
11 | On clicking '+' icon near the Assured name, the screen get refreshed. | Open | fixed | closed | closed
12 | On clicking delete icon against the location, system display alert as "An error occurred while communicating to the server" | Open | fixed | closed | closed
13 | On clicking delete icon against the equipment information, system display alert as "An error occurred while communicating to the server" | Open | fixed | closed | closed
14 | System allow to give premium rate greater than the maximum limit for basic cover and extension cover. | Open | fixed | closed | closed
15 | If multiple records added for Data Media Details and Increase in Cost of Workers system allow to edit/delete only one record. for remaining records, edit/delete buttons are not working. | Open | fixed | re-open | closed
16 | For DATA MEDIA COVER and INCREASED COST OF WORKING COVER of rate% is given less than minimum rate, system not send approval for that. Refer Q/10000/46/24/000963 | Open | fixed | CLOSED | CLOSED
17 | Select Data Media Details and Increased Cost of Working Details in Location 1. The system automatically selects Data Media Details and Increased Cost of Working Details in Locations 2, 3, … n |  |  | Open | CLOSED
18 | Section 1 and Section 3 are selected, but no records are found in the Item Insured dropdown. |  |  | Open | Open
19 | Sections 2 and 3 Checkbox are automatically deselected when the popup is closed. |  |  |  | Open
20 | An error occurs when uploading an Excel file with the same name for different leads (Error: "File Name Already Exists: InventoryUpload.xlsx").