## Revision History
Test case
Revision History
Version No | Date | Reason For Changes | Author | Reviewer | Approver
0.01 | 2024-03-21 | Draft | Anurag Kumar
0.02 | 2024-03-26 | Updated based on review comment | Anurag Kumar | VENKATALAKSHMI
1 | 2024-03-26 | Baseline | Anurag Kumar | VENKATALAKSHMI | Saravana Kumar M
2 | 2024-03-26 | Executed Test Case- Cycle 1 | Anurag Kumar
3 | 2024-03-26 | Executed Test Case- Cycle 2 | Anurag Kumar
Test Case Information
Sl.No | Test case ID | Test Case Objective | Status | Test Scenario Link
1 | TC_C_FinancialEndorsement_001 | To Verify the Policy No field with valid and invalid inputs in motor & fire. | PASS | TS_FinancialEndorsement_002
2 | TC_C_FinancialEndorsement_002 | To Verify the Endorsement SearchBy field with valid and invalid inputs in motor & fire. | PASS | TS_FinancialEndorsement_002
3 | TC_C_FinancialEndorsement_003 | To Verify the Endorsement SearchValue field with valid and invalid inputs in motor & fire. | PASS | TS_FinancialEndorsement_002
4 | TC_C_FinancialEndorsement_004 | To Verify the Endr Calculation Type field with valid and invalid inputs in motor & fire. | PASS | TS_FinancialEndorsement_002
5 | TC_F_FinancialEndorsement_001 | To Check the Functionality "Exclusion of VAT " in Endorsement with Submit button in motor & fire. | PASS | TS_FinancialEndorsement_001
6 | TC_F_FinancialEndorsement_002 | To Check the Functionality "Exclusion of VAT " in Endorsement with Reject button in motor & fire. | PASS | TS_FinancialEndorsement_001

## Component Test Case
Test Case Basic Information | [7 empty] | Test Case Execution Information
Project Name : | NOVA PHIL
Screen Name : | Endorsement Financial
Pre Requisite : | Application should be in Running Condition. | [6 empty] | Testing Type : | System Integration Testing
Instructions : | Launching the URL. Login with Valid Credentials. | [7 empty] | Cycle 1
Testcase ID | Step No. | Sprint Number | Userstory ID | Input Specification | Help / Remarks | Input/Test Data | Expected Result | Actual Result | (Pass/Fail) | Tested By | Tested Date : | Defect Id
To Verify the Policy No field with valid and invalid inputs in motor & fire.
TC_C_FinancialEndorsement_001 | Step1 | 25 | NOVPHILSCR-1395 | To Verify the field "Policy No" with valid input with Search Type as "Policy Number". |  | 10000/11/22/000236 | System should accept the provided valid data in the field "Policy No". | System accept the provided valid data in the field "Policy No". | PASS | Anurag Kumar | 2024-03-21
TC_C_FinancialEndorsement_001 | Step2 | 25 | NOVPHILSCR-1395 | To Verify the field "Policy No" with valid input with Search Type as "Policy Number". |  | 10000/11/22/000048 | System should accept the provided valid data in the field "Policy No". | System accept the provided valid data in the field "Policy No". | PASS | Anurag Kumar | 2024-03-21
TC_C_FinancialEndorsement_001 | Step3 | 25 | NOVPHILSCR-1395 | To Verify the field "Policy No" with invalid input as only Numerals with Search Type as "Policy Number". |  | 10000 | System should not accept the provided invalid data in the field "Policy No". | System not accept the provided invalid data in the field "Policy No". | PASS | Anurag Kumar | 2024-03-21
TC_C_FinancialEndorsement_001 | Step4 | 25 | NOVPHILSCR-1395 | To Verify the field "Policy No" with invalid input as only Numerals with Search Type as "Policy Number". |  | 100001122000048 | System should not accept the provided invalid data in the field "Policy No". | System not accept the provided invalid data in the field "Policy No". | PASS | Anurag Kumar | 2024-03-21
TC_C_FinancialEndorsement_001 | Step5 | 25 | NOVPHILSCR-1395 | To Verify the field "Policy No" with invalid input as character and special character with Search Type as "Policy Number". |  | /P/ | System should not accept the provided invalid data in the field "Policy No". | System not accept the provided invalid data in the field "Policy No". | PASS | Anurag Kumar | 2024-03-21
TC_C_FinancialEndorsement_001 | Step6 | 25 | NOVPHILSCR-1395 | To Verify the field "Policy No" with invalid input as numerals and character with Search Type as "Policy Number". |  | 3121P | System should not accept the provided invalid data in the field "Policy No". | System not accept the provided invalid data in the field "Policy No". | PASS | Anurag Kumar | 2024-03-21
TC_C_FinancialEndorsement_001 | Step7 | 25 | NOVPHILSCR-1395 | To Verify the field "Policy No" with invalid input as characters and numerals with Search Type as "Policy Number". |  | P0000507 | System should not accept the provided invalid data in the field "Policy No". | System not accept the provided invalid data in the field "Policy No". | PASS | Anurag Kumar | 2024-03-21
TC_C_FinancialEndorsement_001 | Step8 | 25 | NOVPHILSCR-1395 | To Verify the field "Policy No" with invalid input as Alphanumerals and Special Characters with Search Type as "Policy Number". |  | 10000_31_21_P_0000507 | System should not accept the provided invalid data in the field "Policy No". | System not accept the provided invalid data in the field "Policy No". | PASS | Anurag Kumar | 2024-03-21
To Verify the Endorsement SearchBy field with valid and invalid inputs in motor & fire.
TC_C_FinancialEndorsement_002 | Step1 | 25 | NOVPHILSCR-1395 | To Verify the field "Endorsement SearchBy" with invalid input from the dropdown |  | --Select-- | System should not accept the provided invalid data in the field "Endorsement SearchBy". | System not accept the provided invalid data in the field "Endorsement SearchBy". | PASS | Anurag Kumar | 2024-03-21
TC_C_FinancialEndorsement_002 | Step2 | 25 | NOVPHILSCR-1395 | To Verify the field "Endorsement SearchBy" with valid input from the dropdown |  | Head | System should accept the provided valid data in the field "Endorsement SearchBy". | System accept the provided valid data in the field "Endorsement SearchBy". | PASS | Anurag Kumar | 2024-03-21
TC_C_FinancialEndorsement_002 | Step3 | 25 | NOVPHILSCR-1395 | To Verify the field "Endorsement SearchBy" with valid input from the dropdown |  | Sub Head | System should accept the provided valid data in the field "Endorsement SearchBy". | System accept the provided valid data in the field "Endorsement SearchBy". | PASS | Anurag Kumar | 2024-03-21
TC_C_FinancialEndorsement_002 | Step4 | 25 | NOVPHILSCR-1395 | To Verify the field "Endorsement SearchBy" with valid input from the dropdown |  | Type | System should accept the provided valid data in the field "Endorsement SearchBy". | System accept the provided valid data in the field "Endorsement SearchBy". | PASS | Anurag Kumar | 2024-03-21
To Verify the Endorsement SearchValue field with valid and invalid inputs in motor & fire.
TC_C_FinancialEndorsement_003 | Step1 | 25 | NOVPHILSCR-1395 | To Verify the field "Endorsement SearchValue" with invalid input from the dropdown |  | --Select-- | System should not accept the provided invalid data in the field "Endorsement SearchValue". | System not accept the provided invalid data in the field "Endorsement SearchValue". | PASS | Anurag Kumar | 2024-03-21
TC_C_FinancialEndorsement_003 | Step2 | 25 | NOVPHILSCR-1395 | To Verify the field "Endorsement SearchValue" with valid input from the dropdown |  | NCB INCLUSION | System should accept the provided valid data in the field "Endorsement SearchValue". | System accept the provided valid data in the field "Endorsement SearchValue". | PASS | Anurag Kumar | 2024-03-21
TC_C_FinancialEndorsement_003 | Step3 | 25 | NOVPHILSCR-1395 | To Verify the field "Endorsement SearchValue" with valid input from the dropdown |  | DECREASE IN SUM INSURED | System should accept the provided valid data in the field "Endorsement SearchValue". | System accept the provided valid data in the field "Endorsement SearchValue". | PASS | Anurag Kumar | 2024-03-21
TC_C_FinancialEndorsement_003 | Step4 | 25 | NOVPHILSCR-1395 | To Verify the field "Endorsement SearchValue" with valid input from the dropdown |  | INCREASE IN SUM INSURED | System should accept the provided valid data in the field "Endorsement SearchValue". | System accept the provided valid data in the field "Endorsement SearchValue". | PASS | Anurag Kumar | 2024-03-21
TC_C_FinancialEndorsement_003 | Step5 | 25 | NOVPHILSCR-1395 | To Verify the field "Endorsement SearchValue" with valid input from the dropdown |  | CORRECT POLICY EXTENSIONS WITH ADDITIONAL PREMIUM | System should accept the provided valid data in the field "Endorsement SearchValue". | System accept the provided valid data in the field "Endorsement SearchValue". | PASS | Anurag Kumar | 2024-03-21
TC_C_FinancialEndorsement_003 | Step6 | 25 | NOVPHILSCR-1395 | To Verify the field "Endorsement SearchValue" with valid input from the dropdown |  | CORRECT SUM INSURED WITH ADDITIONAL PREMIUM | System should accept the provided valid data in the field "Endorsement SearchValue". | System accept the provided valid data in the field "Endorsement SearchValue". | PASS | Anurag Kumar | 2024-03-21
TC_C_FinancialEndorsement_003 | Step7 | 25 | NOVPHILSCR-1395 | To Verify the field "Endorsement SearchValue" with valid input from the dropdown |  | CORRECT SUM INSURED & POLICY EXTENSIONS WITH ADDITIONAL PREMIUM | System should accept the provided valid data in the field "Endorsement SearchValue". | System accept the provided valid data in the field "Endorsement SearchValue". | PASS | Anurag Kumar | 2024-03-21
TC_C_FinancialEndorsement_003 | Step8 | 25 | NOVPHILSCR-1395 | To Verify the field "Endorsement SearchValue" with valid input from the dropdown |  | INCLUSION OF PD COVERAGE | System should accept the provided valid data in the field "Endorsement SearchValue". | System accept the provided valid data in the field "Endorsement SearchValue". | PASS | Anurag Kumar | 2024-03-21
TC_C_FinancialEndorsement_003 | Step9 | 25 | NOVPHILSCR-1395 | To Verify the field "Endorsement SearchValue" with valid input from the dropdown |  | INCLUSION OF BI COVERAGE | System should accept the provided valid data in the field "Endorsement SearchValue". | System accept the provided valid data in the field "Endorsement SearchValue". | PASS | Anurag Kumar | 2024-03-21
TC_C_FinancialEndorsement_003 | Step10 | 25 | NOVPHILSCR-1395 | To Verify the field "Endorsement SearchValue" with valid input from the dropdown |  | CHANGE IN PD COVERAGE | System should accept the provided valid data in the field "Endorsement SearchValue". | System accept the provided valid data in the field "Endorsement SearchValue". | PASS | Anurag Kumar | 2024-03-21
TC_C_FinancialEndorsement_003 | Step11 | 25 | NOVPHILSCR-1395 | To Verify the field "Endorsement SearchValue" with valid input from the dropdown |  | CHANGE IN BI COVERAGE | System should accept the provided valid data in the field "Endorsement SearchValue". | System accept the provided valid data in the field "Endorsement SearchValue". | PASS | Anurag Kumar | 2024-03-21
TC_C_FinancialEndorsement_003 | Step12 | 25 | NOVPHILSCR-1395 | To Verify the field "Endorsement SearchValue" with valid input from the dropdown |  | CHANGE IN USE ( eg. PRIVATE USE TO TNVS or TNVS to Private use) | System should accept the provided valid data in the field "Endorsement SearchValue". | System accept the provided valid data in the field "Endorsement SearchValue". | PASS | Anurag Kumar | 2024-03-21
TC_C_FinancialEndorsement_003 | Step13 | 25 | NOVPHILSCR-1395 | To Verify the field "Endorsement SearchValue" with valid input from the dropdown |  | INCLUSION OF ACCESSORIES | System should accept the provided valid data in the field "Endorsement SearchValue". | System accept the provided valid data in the field "Endorsement SearchValue". | PASS | Anurag Kumar | 2024-03-21
TC_C_FinancialEndorsement_003 | Step14 | 25 | NOVPHILSCR-1395 | To Verify the field "Endorsement SearchValue" with valid input from the dropdown |  | INCLUSION OF AUTO PA (APA) WITH ADDITIONAL PREMIUM | System should accept the provided valid data in the field "Endorsement SearchValue". | System accept the provided valid data in the field "Endorsement SearchValue". | PASS | Anurag Kumar | 2024-03-21
TC_C_FinancialEndorsement_003 | Step15 | 25 | NOVPHILSCR-1395 | To Verify the field "Endorsement SearchValue" with valid input from the dropdown |  | INCLUSION OF AOG COVERAGE (WITH ADDITIONAL PREMIUM) | System should accept the provided valid data in the field "Endorsement SearchValue". | System accept the provided valid data in the field "Endorsement SearchValue". | PASS | Anurag Kumar | 2024-03-21
TC_C_FinancialEndorsement_003 | Step16 | 25 | NOVPHILSCR-1395 | To Verify the field "Endorsement SearchValue" with valid input from the dropdown |  | CHANGE IN POLICY PERIOD | System should accept the provided valid data in the field "Endorsement SearchValue". | System accept the provided valid data in the field "Endorsement SearchValue". | PASS | Anurag Kumar | 2024-03-21
TC_C_FinancialEndorsement_003 | Step17 | 25 | NOVPHILSCR-1395 | To Verify the field "Endorsement SearchValue" with valid input from the dropdown |  | CHANGE IN DATE OF FIRST REGISTRATION | System should accept the provided valid data in the field "Endorsement SearchValue". | System accept the provided valid data in the field "Endorsement SearchValue". | PASS | Anurag Kumar | 2024-03-21
TC_C_FinancialEndorsement_003 | Step18 | 25 | NOVPHILSCR-1395 | To Verify the field "Endorsement SearchValue" with valid input from the dropdown |  | CORRECT VEHICLE DESCRIPTION (MAKE AND MODEL) | System should accept the provided valid data in the field "Endorsement SearchValue". | System accept the provided valid data in the field "Endorsement SearchValue". | PASS | Anurag Kumar | 2024-03-21
TC_C_FinancialEndorsement_003 | Step19 | 25 | NOVPHILSCR-1395 | To Verify the field "Endorsement SearchValue" with valid input from the dropdown |  | CHANGE IN FAIR MARKET VALUE (FMV) | System should accept the provided valid data in the field "Endorsement SearchValue". | System accept the provided valid data in the field "Endorsement SearchValue". | PASS | Anurag Kumar | 2024-03-21
To Verify the Endr Calculation Type field with valid and invalid inputs in motor & fire.
TC_C_FinancialEndorsement_004 | Step1 | 25 | NOVPHILSCR-1395 | To Verify the field "Endr Calculation Type" with Null Input from the dropdown. |  | --Select-- | System should not accept the provided invalid data in the field "Endr Calculation Type". | System not accept the provided invalid data in the field "Endr Calculation Type". | PASS | Anurag Kumar | 2024-03-21
TC_C_FinancialEndorsement_004 | Step2 | 25 | NOVPHILSCR-1395 | To Verify the field "Endr Calculation Type" with valid input from the dropdown. |  | Full | System should accept the provided valid data in the field "Endr Calculation Type". | System accept the provided valid data in the field "Endr Calculation Type". | PASS | Anurag Kumar | 2024-03-21
TC_C_FinancialEndorsement_004 | Step3 | 25 | NOVPHILSCR-1395 | To Verify the field "Endr Calculation Type" with Valid Input from the dropdown. |  | Long Term | System should accept the provided valid data in the field "Endr Calculation Type". | System accept the provided valid data in the field "Endr Calculation Type". | PASS | Anurag Kumar | 2024-03-21
TC_C_FinancialEndorsement_004 | Step4 | 25 | NOVPHILSCR-1395 | To Verify the field "Endr Calculation Type" with valid input from the dropdown. |  | Short Period | System should accept the provided valid data in the field "Endr Calculation Type". | System accept the provided valid data in the field "Endr Calculation Type". | PASS | Anurag Kumar | 2024-03-21
TC_C_FinancialEndorsement_004 | Step5 | 25 | NOVPHILSCR-1395 | To Verify the field "Endr Calculation Type" with valid input from the dropdown. |  | Full / Pro-Rata | System should accept the provided valid data in the field "Endr Calculation Type". | System accept the provided valid data in the field "Endr Calculation Type". | PASS | Anurag Kumar | 2024-03-21
TC_C_FinancialEndorsement_004 | Step6 | 25 | NOVPHILSCR-1395 | To Verify the field "Endr Calculation Type" with valid input from the dropdown. |  | Prorata / Short Period | System should accept the provided valid data in the field "Endr Calculation Type". | System accept the provided valid data in the field "Endr Calculation Type". | PASS | Anurag Kumar | 2024-03-21
TC_C_FinancialEndorsement_004 | Step7 | 25 | NOVPHILSCR-1395 | To Verify the field "Endr Calculation Type" with valid input from the dropdown. |  | Full / Pro-Rata / Short Period | System should accept the provided valid data in the field "Endr Calculation Type". | System accept the provided valid data in the field "Endr Calculation Type". | PASS | Anurag Kumar | 2024-03-21
Note on M6: SEPG: Defect Id to be entered against Failed steps

## Functional Test Case
Test Case Basic Information | [7 empty] | Test Case Execution Information
Project Name : | NOVA PHIL
Screen Name : | Endorsement Financial
Pre Requisite : | Application should be in Running Condition. | [6 empty] | Testing Type : | System Integration Testing |  |  |  | System Integration Testing
Instructions : | Launching the URL. Login with Valid Credentials. | [7 empty] | Cycle 1 |  |  |  | Cycle 2
Testcase ID | Step No. | Sprint Number | Userstory ID | Input Specification | Help / Remarks | Input/Test Data | Expected Result | Actual Result | (Pass/Fail) | Tested By | Tested Date : | Defect Id | (Pass/Fail) | Tested By | Tested Date : | Defect Id
To Check the Functionality "Exclusion of VAT " in Endorsement with Submit button in motor & fire.
TC_F_FinancialEndorsement_001 | Step 1 | 25 | NOVPHILSCR-1395 | Navigate to Endorsement Financial Screen. | 1. Select "Endorsement financial" under the Main Menu "Endorsement" (or) 2. Enter "Endorsement Financial" in the Menu Search and select the Search Result. | <No Input> | 1. On Selecting the menu, System should display the Policy Search Screen. 2. System should display the Policy No. field with "Go" and "Close" button in the screen. | 1. On selecting the menu, System displays the Policy Search Screen. 2. System displays the Policy No. field with "Go" and "Close" button in the screen. | PASS | Anurag Kumar | 2024-03-21 |  | PASS | Anurag Kumar | 2022-07-26
TC_F_FinancialEndorsement_001 | Step 2 | 25 | NOVPHILSCR-1395 | Enter value in the field "Policy No". | <No Remarks> | PolicyNo: 10003/31/20/000344 | System should accept the entered values in the respective field. | System accepts the entered values in the respective field. | PASS | Anurag Kumar | 2024-03-21 |  | PASS | Anurag Kumar | 2022-07-26
TC_F_FinancialEndorsement_001 | Step 3 | 25 | NOVPHILSCR-1395 | Click on "Go" button. | Click on the Go button available in the screen. | <No Input> | On Clicking the "Go" button, System should accept the value in the Policy Number field and should display the Endorsement Request screen with following details: 1. Policy Information Link. 2. Financial Endorsement List with Columns as "Head, Sub Head, PI required, Approval Required". 3. Search Criterias to search the repsctive Endorsement Type. | On Clicking the "Go" button, System accepts the value in the Policy Number field and displays the Endorsement Request screen with following details: 1. Policy Information Link. 2. Financial Endorsement List with Columns as "Head, Sub Head, PI required, Approval Required". 3. Search Criterias to search the repsctive Endorsement Type. | PASS | Anurag Kumar | 2024-03-21 |  | PASS | Anurag Kumar | 2022-07-26
TC_F_FinancialEndorsement_001 | Step 4 | 25 | NOVPHILSCR-1395 | Verify the details in the "Policy Info" Link. | <No Remarks> | <No Input> | On Clicking the "Policy Info" Link, System should display the Policy Information window with Policy details under the headers: 1. Basic Information. 2. Insured Details. 3. Vehicle Details. 4. Business Source. 5. List of Opted Coverages. 6. Ownership Change details. 7. Policy Extension Details. 8. Endorsement Details. 9. Previous Policy Info. 10. Financier Information. | On Clicking the "Policy Info" Link, System displays the Policy Information window with Policy details under the headers: 1. Basic Information. 2. Insured Details. 3. Vehicle Details. 4. Business Source. 5. List of Opted Coverages. 6. Ownership Change details. 7. Policy Extension Details. 8. Endorsement Details. 9. Previous Policy Info. 10. Financier Information. | PASS | Anurag Kumar | 2024-03-21 |  | PASS | Anurag Kumar | 2022-07-26
TC_F_FinancialEndorsement_001 | Step 5 | 25 | NOVPHILSCR-1395 | Click on Close button in the Policy Information window. | <No Remarks> | <No Input> | On Clicking the Close button, System should close the Policy Information window. | On Clicking the Close button, System closes the Policy Information window. | PASS | Anurag Kumar | 2024-03-21 |  | PASS | Anurag Kumar | 2022-07-26
TC_F_FinancialEndorsement_001 | Step 6 | 25 | NOVPHILSCR-1395 | Search the Respective Endorsement Sub Type. | 1. Select the Value in the Search By field. 2. Enter valid input in the Search Value field. 3. Click on Search button. | Search By : Sub Head Search Value : Exclusion of VAT | System should accept the provided value in the respective fields and on Clicking the "Search" button, System should display the search result in the grid. | System accepts the provided value in the respective fields and on Clicking the "Search" button, System displays the search result in the grid. | PASS | Anurag Kumar | 2024-03-21 |  | PASS | Anurag Kumar | 2022-07-26
TC_F_FinancialEndorsement_001 | Step 7 | 25 | NOVPHILSCR-1395 | Provide inputs in the below mentioned fields. 1. Calculation Type. 2. Request Date. 3. Effective From Date. | <No Remarks> | Calculation Type: Full | 1. System should display the Calculation Type based on the Product and the Endorsement Sub Head selected. 2. On Selecting the Calculation Type as "Full", System should autodisplay the Effective From Date as "Policy Start Date". 3. On Selecting the Calculation Type as "Prorata", System should autodisplay the Effective From Date as "Current Date". 4. Effective To should always be displayed as "Policy End Date". | 1. System displays the Calculation Type based on the Product and the Endorsement Sub Head selected. 2. On Selecting the Calculation Type as "Full", System autodisplays the Effective From Date as "Policy Start Date". 3. On Selecting the Calculation Type as "Prorata", System autodisplays the Effective From Date as "Current Date". 4. Effective To field always be displayed as "Policy End Date". | PASS | Anurag Kumar | 2024-03-21 |  | PASS | Anurag Kumar | 2022-07-26
TC_F_FinancialEndorsement_001 | Step 8 | 25 | NOVPHILSCR-1395 | Click on "Proceed" button. | <No Remarks> | <No Input> | On Clicking the "Proceed" button, System should display the Endorsement Screen with following details: 1. System should autodisplay all the fields in the screen and should be in the uneditable mode. 2. System should display the "Previous Details" button in the screen. 3. System should enable only the Commission related fields in the screen. 4. System should display the "Save, Submit, Reject, Download Quote, Download Schedule, and Close" button. | On Clicking the "Proceed" button, System displays the Endorsement Screen with following details: 1. System autodisplays all the fields in the screen and should be in the uneditable mode. 2. System displays the "Previous Details" button in the screen. 3. System enables only the Commission related fields in the screen. 4. System displays the "Save, Submit, Reject, Download Quote, Download Schedule, and Close" button. | PASS | Anurag Kumar | 2024-03-21 |  | PASS | Anurag Kumar | 2022-07-26
TC_F_FinancialEndorsement_001 | Step 9 | 25 | NOVPHILSCR-1395 | Click on "Previous Details" button. | <No Remarks> | <No Input> | On Clicking the "Previous Details" button, System should display the Previous Comission information provided in the Policy. | On Clicking the "Previous Details" button, System displays the Previous Comission information provided in the Policy. | PASS | Anurag Kumar | 2024-03-21 |  | PASS | Anurag Kumar | 2022-07-26
TC_F_FinancialEndorsement_001 | Step 10 | 25 | NOVPHILSCR-1395 | Click on "Close" button in the Previous details window. | <No Remarks> | <No Input> | On Clicking the Close button, System should close the Previous details window. | On Clicking the Close button, System closes the Previous details window. | PASS | Anurag Kumar | 2024-03-21 |  | PASS | Anurag Kumar | 2022-07-26
TC_F_FinancialEndorsement_001 | Step 11 | 25 | NOVPHILSCR-1395 | Click on "No Claim Bonus Certificate" radio button. | <No Remarks> | No Claim Bonus Certificate:Yes | System should enable the below fields: 1.NCB Certificate Date 2.Reference number 3.NCB Percentage | System enables the below fields: 1.NCB Certificate Date 2.Reference number 3.NCB Percentage | PASS | Anurag Kumar | 2024-03-21 |  | PASS | Anurag Kumar | 2022-07-26
TC_F_FinancialEndorsement_001 | Step 12 | 25 | NOVPHILSCR-1395 | Enter the below mentioned fields with the valid inputs: 1.VAT Exempt | <No Remarks> | <Click> | System should accept the entered values in the respective field.System should allow to select the check box if the check box is not selected in the Original policy or Previous endorsement. | System accepts the entered values in the respective field.System is allowing to select the check box if the check box is not selected in the Original policy or Previous endorsement. | PASS | Anurag Kumar | 2024-03-21 |  | PASS | Anurag Kumar | 2022-07-26
TC_F_FinancialEndorsement_001 | Step 13 | 25 | NOVPHILSCR-1395 | Click on "Gross Premium" link. | <No Remarks> | <No Input> | 1. On Clicking the "Gross Premium" link, System should autodispaly the "Gross Premium, Difference in Premium" value. 2. For Sub Head type as "Exclusion of VAT", System should autodisplay the Gross Premium of the Policy without any change and the Difference in Premium should be zero. | 1. On Clicking the "Gross Premium" link, System autodisplays the "Gross Premium, Difference in Premium" value. 2. For Sub Head type as "Exclusion of VAT", System autodisplays the Gross Premium of the Policy without any change and the Difference in Premium displayed as zero. | PASS | Anurag Kumar | 2024-03-21 |  | PASS | Anurag Kumar | 2022-07-26
TC_F_FinancialEndorsement_001 | Step 14 | 25 | NOVPHILSCR-1395 | Provide input in the field "Endorsement Fee". | <No Remarks> | Endorsement Fee : 50 | System should accept the provided input in the field. | System accepts the provided input in the field. | PASS | Anurag Kumar | 2024-03-21 |  | PASS | Anurag Kumar | 2022-07-26
TC_F_FinancialEndorsement_001 | Step 15 | 25 | NOVPHILSCR-1395 | Click on "Save" button. | Click on the Save button available in the screen. | <No Input> | 1. On Clicking on the Save button, System should save the updated details and should display the alert message with Endorsement Reference Number and on clicking "Ok" button in the alert message, System should display the Endorsement screen. 2. Endorsement Reference Number should be Policy Number followed by Number of Endorsements. 3. System should enable the "Submit, Reject" button. | 1. On Clicking on the Save button, System saves the updated details and displays the alert message as "Endorsement Saved Successfully. Endorsement Reference No:10003/31/20/000344-010" and on clicking "Ok" button in the alert message, System moves to the Endorsement screen. 2. System enables the "Submit, Reject" button. | FAIL | Anurag Kumar | 2024-03-21 | NOVPHILSCR-1470 | PASS | Anurag Kumar | 2022-07-26
TC_F_FinancialEndorsement_001 | Step 16 | 25 | NOVPHILSCR-1395 | Click on "Submit" button. | Click on the Submit button available in the screen. | <No Input> | 1. On Clicking on the Submit button, System should submit the updated details and should display the alert message with Endorsement Reference Number and on clicking "Ok" button in the alert message, System should display the Endorsement screen. 2. Endorsement Reference Number should be Policy Number followed by Number of Endorsements. | On Clicking on the Save button, System saves the updated details and displays the alert message as "Endorsement Saved Successfully. Endorsement Reference No:10003/31/20/000344-010" and on clicking "Ok" button in the alert message, System moves to the Endorsement screen. | PASS | Anurag Kumar | 2024-03-21 |  | PASS | Anurag Kumar | 2022-07-26
TC_F_FinancialEndorsement_001 | Step 17 | 25 | NOVPHILSCR-1395 | Click on "Close" button. | <No Remarks> | <No Input> | On Clicking the "Close" button, System should Close the respective endorsement details and should move to the Dashboard screen. | On Clicking the "Close" button, System Closes the respective endorsement details and it moves to the Dashboard screen. | PASS | Anurag Kumar | 2024-03-21 |  | PASS | Anurag Kumar | 2022-07-26
To Check the Functionality "Exclusion of VAT " in Endorsement with Reject button in motor & fire.
TC_F_FinancialEndorsement_002 | Step 1 | 25 | NOVPHILSCR-1395 | Navigate to Endorsement Financial Screen. | 1. Select "Endorsement financial" under the Main Menu "Endorsement" (or) 2. Enter "Endorsement Financial" in the Menu Search and select the Search Result. | <No Input> | 1. On Selecting the menu, System should display the Policy Search Screen. 2. System should display the Policy No. field with "Go" and "Close" button in the screen. | 1. On selecting the menu, System displays the Policy Search Screen. 2. System displays the Policy No. field with "Go" and "Close" button in the screen. | PASS | Anurag Kumar | 2024-03-21 |  | PASS | Anurag Kumar | 2022-07-26
TC_F_FinancialEndorsement_002 | Step 2 | 25 | NOVPHILSCR-1395 | Enter value in the field "Policy No". | <No Remarks> | PolicyNo: 10003/31/20/000344 | System should accept the entered values in the respective field. | System accepts the entered values in the respective field. | PASS | Anurag Kumar | 2024-03-21 |  | PASS | Anurag Kumar | 2022-07-26
TC_F_FinancialEndorsement_002 | Step 3 | 25 | NOVPHILSCR-1395 | Click on "Go" button. | Click on the Go button available in the screen. | <No Input> | On Clicking the "Go" button, System should accept the value in the Policy Number field and should display the Endorsement Request screen with following details: 1. Policy Information Link. 2. Financial Endorsement List with Columns as "Head, Sub Head, PI required, Approval Required". 3. Search Criterias to search the repsctive Endorsement Type. | On Clicking the "Go" button, System accepts the value in the Policy Number field and displays the Endorsement Request screen with following details: 1. Policy Information Link. 2. Financial Endorsement List with Columns as "Head, Sub Head, PI required, Approval Required". 3. Search Criterias to search the repsctive Endorsement Type. | PASS | Anurag Kumar | 2024-03-21 |  | PASS | Anurag Kumar | 2022-07-26
TC_F_FinancialEndorsement_002 | Step 4 | 25 | NOVPHILSCR-1395 | Verify the details in the "Policy Info" Link. | <No Remarks> | <No Input> | On Clicking the "Policy Info" Link, System should display the Policy Information window with Policy details under the headers: 1. Basic Information. 2. Insured Details. 3. Vehicle Details. 4. Business Source. 5. List of Opted Coverages. 6. Ownership Change details. 7. Policy Extension Details. 8. Endorsement Details. 9. Previous Policy Info. 10. Financier Information. | On Clicking the "Policy Info" Link, System displays the Policy Information window with Policy details under the headers: 1. Basic Information. 2. Insured Details. 3. Vehicle Details. 4. Business Source. 5. List of Opted Coverages. 6. Ownership Change details. 7. Policy Extension Details. 8. Endorsement Details. 9. Previous Policy Info. 10. Financier Information. | PASS | Anurag Kumar | 2024-03-21 |  | PASS | Anurag Kumar | 2022-07-26
TC_F_FinancialEndorsement_002 | Step 5 | 25 | NOVPHILSCR-1395 | Click on Close button in the Policy Information window. | <No Remarks> | <No Input> | On Clicking the Close button, System should close the Policy Information window. | On Clicking the Close button, System closes the Policy Information window. | PASS | Anurag Kumar | 2024-03-21 |  | PASS | Anurag Kumar | 2022-07-26
TC_F_FinancialEndorsement_002 | Step 6 | 25 | NOVPHILSCR-1395 | Search the Respective Endorsement Sub Type. | 1. Select the Value in the Search By field. 2. Enter valid input in the Search Value field. 3. Click on Search button. | Search By : Sub Head Search Value : Exclusion of VAT | System should accept the provided value in the respective fields and on Clicking the "Search" button, System should display the search result in the grid. | System accepts the provided value in the respective fields and on Clicking the "Search" button, System displays the search result in the grid. | PASS | Anurag Kumar | 2024-03-21 |  | PASS | Anurag Kumar | 2022-07-26
TC_F_FinancialEndorsement_002 | Step 7 | 25 | NOVPHILSCR-1395 | Provide inputs in the below mentioned fields. 1. Calculation Type. 2. Request Date. 3. Effective From Date. | <No Remarks> | Calculation Type: Full | 1. System should display the Calculation Type based on the Product and the Endorsement Sub Head selected. 2. On Selecting the Calculation Type as "Full", System should autodisplay the Effective From Date as "Policy Start Date". 3. On Selecting the Calculation Type as "Prorata", System should autodisplay the Effective From Date as "Current Date". 4. Effective To should always be displayed as "Policy End Date". | 1. System displays the Calculation Type based on the Product and the Endorsement Sub Head selected. 2. On Selecting the Calculation Type as "Full", System autodisplays the Effective From Date as "Policy Start Date". 3. On Selecting the Calculation Type as "Prorata", System autodisplays the Effective From Date as "Current Date". 4. Effective To field always be displayed as "Policy End Date". | PASS | Anurag Kumar | 2024-03-21 |  | PASS | Anurag Kumar | 2022-07-26
TC_F_FinancialEndorsement_002 | Step 8 | 25 | NOVPHILSCR-1395 | Click on "Proceed" button. | <No Remarks> | <No Input> | On Clicking the "Proceed" button, System should display the Endorsement Screen with following details: 1. System should autodisplay all the fields in the screen and should be in the uneditable mode. 2. System should display the "Previous Details" button in the screen. 3. System should enable only the Commission related fields in the screen. 4. System should display the "Save, Submit, Reject, Download Quote, Download Schedule, and Close" button. | On Clicking the "Proceed" button, System displays the Endorsement Screen with following details: 1. System autodisplays all the fields in the screen and should be in the uneditable mode. 2. System displays the "Previous Details" button in the screen. 3. System enables only the Commission related fields in the screen. 4. System displays the "Save, Submit, Reject, Download Quote, Download Schedule, and Close" button. | PASS | Anurag Kumar | 2024-03-21 |  | PASS | Anurag Kumar | 2022-07-26
TC_F_FinancialEndorsement_002 | Step 9 | 25 | NOVPHILSCR-1395 | Click on "Previous Details" button. | <No Remarks> | <No Input> | On Clicking the "Previous Details" button, System should display the Previous Comission information provided in the Policy. | On Clicking the "Previous Details" button, System displays the Previous Comission information provided in the Policy. | PASS | Anurag Kumar | 2024-03-21 |  | PASS | Anurag Kumar | 2022-07-26
TC_F_FinancialEndorsement_002 | Step 10 | 25 | NOVPHILSCR-1395 | Click on "Close" button in the Previous details window. | <No Remarks> | <No Input> | On Clicking the Close button, System should close the Previous details window. | On Clicking the Close button, System closes the Previous details window. | PASS | Anurag Kumar | 2024-03-21 |  | PASS | Anurag Kumar | 2022-07-26
TC_F_FinancialEndorsement_002 | Step 11 | 25 | NOVPHILSCR-1395 | Click on "No Claim Bonus Certificate" radio button. | <No Remarks> | No Claim Bonus Certificate:Yes | System should enable the below fields: 1.NCB Certificate Date 2.Reference number 3.NCB Percentage | System enables the below fields: 1.NCB Certificate Date 2.Reference number 3.NCB Percentage | PASS | Anurag Kumar | 2024-03-21 |  | PASS | Anurag Kumar | 2022-07-26
TC_F_FinancialEndorsement_002 | Step 12 | 25 | NOVPHILSCR-1395 | Enter the below mentioned fields with the valid inputs: 1.VAT Exempt | <No Remarks> | <Click> | System should accept the entered values in the respective field.System should allow to select the check box if the check box is not selected in the Original policy or Previous endorsement. | System accepts the entered values in the respective field.System is allowing to select the check box if the check box is not selected in the Original policy or Previous endorsement. | PASS | Anurag Kumar | 2024-03-21 |  | PASS | Anurag Kumar | 2022-07-26
TC_F_FinancialEndorsement_002 | Step 13 | 25 | NOVPHILSCR-1395 | Click on "Gross Premium" link. | <No Remarks> | <No Input> | 1. On Clicking the "Gross Premium" link, System should autodispaly the "Gross Premium, Difference in Premium" value. 2. For Sub Head type as "Exclusion of VAT", System should autodisplay the Gross Premium of the Policy without any change and the Difference in Premium should be zero. | 1. On Clicking the "Gross Premium" link, System autodisplays the "Gross Premium, Difference in Premium" value. 2. For Sub Head type as "Exclusion of VAT", System autodisplays the Gross Premium of the Policy without any change and the Difference in Premium displayed as zero. | PASS | Anurag Kumar | 2024-03-21 |  | PASS | Anurag Kumar | 2022-07-26
TC_F_FinancialEndorsement_002 | Step 14 | 25 | NOVPHILSCR-1395 | Provide input in the field "Endorsement Fee". | <No Remarks> | Endorsement Fee : 50 | System should accept the provided input in the field. | System accepts the provided input in the field. | PASS | Anurag Kumar | 2024-03-21 |  | PASS | Anurag Kumar | 2022-07-26
TC_F_FinancialEndorsement_002 | Step 15 | 25 | NOVPHILSCR-1395 | Click on "Save" button. | Click on the Save button available in the screen. | <No Input> | 1. On Clicking on the Save button, System should save the updated details and should display the alert message with Endorsement Reference Number and on clicking "Ok" button in the alert message, System should display the Endorsement screen. 2. Endorsement Reference Number should be Policy Number followed by Number of Endorsements. 3. System should enable the "Submit, Reject" button. | 1. On Clicking on the Save button, System saves the updated details and displays the alert message as "Endorsement Saved Successfully. Endorsement Reference No:10003/31/20/000344-010" and on clicking "Ok" button in the alert message, System moves to the Endorsement screen. 2. System enables the "Submit, Reject" button. | PASS | Anurag Kumar | 2024-03-21 |  | PASS | Anurag Kumar | 2022-07-26
TC_F_FinancialEndorsement_002 | Step 16 | 25 | NOVPHILSCR-1395 | Click on "Reject" button. | <No Remarks> | <No Input> | On Clicking the "Reject" button, System should reject the respective endorsement details and should move to the Dashboard screen. | On Clicking the "Reject" button, System rejects the respective endorsement details and moves to the Dashboard screen. | PASS | Anurag Kumar | 2024-03-21 |  | PASS | Anurag Kumar | 2022-07-26
TC_F_FinancialEndorsement_002 | Step 17 | 25 | NOVPHILSCR-1395 | Click on "Close" button. | <No Remarks> | <No Input> | On Clicking the "Close" button, System should Close the respective endorsement details and should move to the Dashboard screen. | On Clicking the "Close" button, System Closes the respective endorsement details and it moves to the Dashboard screen. | PASS | Anurag Kumar | 2024-03-21 |  | PASS | Anurag Kumar | 2022-07-26
Note on M6: SEPG: Defect Id to be entered against Failed steps
Note on Q6: SEPG: Defect Id to be entered against Failed steps